## Main
Security | Security Issues | Last Update | Notes:
Security | Security Issues | 2015-11-16 | Last night while I was waiting for security around 7:10PM. A group of teenagers were on the property after 7PM. I asked them to leave the property because it was after hours. The teenagers left without any issues but the were smoking an illegal substance,
Project ID | Large Projects By Contractors | Last Update | Notes:
0
2015-L01 | Seperation of Water Services CMFS | 0
2015-L02 | Seperation of Gas Services CMFS | 0 | 0
2015-L03 | Seperation of Electrical Services CMFS | 2015-11-18 | Summary: Installation complete. Awaiting Pepco to begin service, possibly Saturday. CFMS will be notified of any disruptions of service.
2015-L04 | Paint Great Hall Exterior(Portico & Trim) Evaluate gutters and do minor repairs. | 2015-11-18 | Site Visit Potomac Chevy Chase Painting, jane whoever 202-505-xxxx. Southernmost column needs $15,000 replacement (termite infestation). Bid expected 11/20/15.
Project ID | Small Projects By Contractors | Last Update | Notes:
2015-S01 | Dining Hall Floor Maintenance | 2015-11-18 | Summary: Floors complete. Polyeurothane coating could not be removed in the hallways. We will strip this during next cleaning.
|  | 2015-11-05 | Scher Flooring Services will complete floor restoration. Total $1307.00
|  | 2015-11-04 | Floors strip and wax started but could not be completed. There is a polyeurothane coating that needs to be removed.
|  | 2015-11-03 | Contractor bid received by email on 11/??/15 at 3:28 pm. Total price $750???
|  | 2015-11-02 | Contractor site visit.
|  | 2015-11-01 | Contacted John Doe 202-505-xxxx to strip and wax basement floors.
2015-S02 | Balancing of Air Flow
2015-S03 | Water Tank Replacement ( Service Buil)
2015-S04 | Water Tank Replacement (Cottage)
2015-S05 | Overhead doors
Status: | Equipment Mantenance | Last Update | Notes:
Waste Disposal Contract
Back Hoe Repair
| Copier Contract | 2015-10-15 | Questions resolved. Spreadsheet updated.
|  | 2015-10-13 | Spreadsheet of copier contract details provided to ALB (Allan, Larry, Brandon). ALB had additional questions to be investigated.
| New Security Contract | 2015-10-20 | I have requested quotes from the following vendors: XXXX, contact name and phone; YYYY, contact name and phone, ZZZZ, contact name and phone
| Trusted Security | 2015-10-22 | Meeting with Trusted Security to discuss ongoing issues (who was there?). Security was not announcing their presence during business hours. Security was not securing offices after business hours. Security was not present during emergencies. Rubio Robinson the General Manager of Trusted Security was issued standard orders for security guards.
|  | 2015-11-17 | Earlena called out today at 10:45AM. I call Trusted Security at 10:50AM. I spoke with Rudio Robinson the manager of Trusted Security and a security guard will on site at 3:00PM until 9:30PM.
| Innovative Security Contract | 2015-11-18 | Contract terminated. Asked to submit bid.
|  | 2015-10-12 | Issued letter of termination, 61 days before contract expired (within 60-day notice required).
|  | 2015-10-01 | Fr. Allan asked that I terminate Innovative Security Contract. It needs to be sent 60 days before contract expires.
Status: | Project By Crew: | Last Update | Notes:
Install Water Service Covers
Headstone Placement
Powerwash All Headstones
Reline Bronze Markers
Top soil dead areas

## Security
Link to Main
Project ID | Project By Contractors: | Last Update | Notes:
Security | Security Issues | 2015-11-16 | Last night while I was waiting for security around 7:10PM. A group of teenagers were on the property after 7PM. I asked them to leave the property because it was after hours. The teenagers left without any issues but the were smoking an illegal substance,

## 2015-L01
Link to Main
Project ID | Project By Contractors: | Due Date: | Notes:
2015-L01 | Seperation of Water Services CMFS

## 2015-L02
Link to Main
Project ID | Project By Contractors: | Due Date: | Notes:
2015-L02 | Seperation of Gas Services CMFS

## 2015-L03
Link to Main
Project ID | Project By Contractors: | Last Update | Notes:
2015-L03 | Seperation of Electrical Services CMFS | 2015-11-18 | Summary: Installation complete. Awaiting Pepco to begin service, possibly Saturday. CFMS will be notified of any disruptions of service.
|  | 2015-11-18 | Kelly and Son's was awarded the contract to separate SPRC and CFMS electrical service.
|  | 2015-11-18 | Kelly and Son’s has finished the installation on the separation unit and awaiting for the senior project manager to inspect the newly installed unit. Once Kelly and son’s senior project manager has approved the inspection. The senior project manager forwards the approval to Pepco so that that can complete the separation. The separation of electricity will be completed on a Saturday and will take up to eight hours to complete. Kelly and Son’s technician will inform me on what Saturday is the best time. I will notify the school before the official separation takes place.

## 2015-L04
Link to Main
Project ID | Project By Contractors: | Last Update | Notes:
2015-L04 | Paint Great Hall Exterior(Portico & Trim) Evaluate gutters and do minor repairs. | 2015-11-18 | Summary: 2 site visits: Potomac Chevy Chase Painting and Premiere Painting. Bids expected 11/20/15.
|  | 2015-11-18 | Site Visit Potomac Chevy Chase Painting, jane whoever 202-505-xxxx. Southernmost column needs $15,000 replacement (termite infestation). Bid expected 11/20/15.
|  | 2015-11-18 | Site Premiere Painting, joe schmo 202-505-xxxx. Southernmost column needs $20,000 replacement (termite infestation). Bid expected 11/20/15.