## budget
| Total budget |  |  |  |  | 335792.4 | 185859 |  | 332953.27 | Target < $300,000 !!!
Division | Description | qty | unit cost | Paid Date | Paid Check | Actual | Actual OMF Contractor | Actual Subtotals | My Budget | Notes
Pre 1: | Architect and Permits
Budget
34292.14
Actual
39374.16
| Ahmann: SE Application Fee, remaining balance |  |  | 2015-12-10 | bill pay | 829.45 |  |  |  | Email invoice 12/05/14
| Ahmann: Zoning Relief Phase (Phase 3), retainer applied |  |  | 2014-11-18 | bill pay | 1109.08 |  |  |  | Email invoice 11/12/14
| Ahmann: Zoning Analysis and Design (Phase 2) |  |  | 2014-08-15 | bill pay | 3668 |  |  |  | Can't find
| Ahmann: Measured Drawings (Phase 1) |  |  | 2014-07-03 | bill pay | 2810.5 |  |  |  | Email invoice 6/27/15
| Ahmann: Retainer |  |  | 2014-06-17 | 2099 | 2000 |  |  |  | Original Contract: email 5/14/14
| Ahmann | [6 empty] | 10417.03 | 9850
| United Structural Engineers, Inc.: Site visit inspect framing |  |  | 2016-03-29 | HELOC, 109 | 500 |  |  |  | Sent check by mail 3/29, waiting for receipt
| Ahmann: Review Doors & Windows purchase, Party Wall Change Order |  |  | 2016-03-16 | HELOC, 107 | 412.5 |  |  |  | Email invoice 3/21/16
| Ahmann: Permints complete |  |  | 2015-11-23 | HELOC, 8002 | 2130.13
| Ahmann: Permits near completion |  |  | 2015-09-08 | bill pay | 2400.36 |  |  |  | Email invoice 6/24/15
| Ahmann: Construction Plans |  |  | 2015-06-29 | 2139 | 6875
| Ahmann: Structural Engineering |  |  | 2015-06-29 | 2139 | 2000
| Ahmann: Construction Plans |  |  | 2015-05-11 | bill pay | 6197 |  |  |  | Paper Invoice and email
| Ahmann: Retainer |  |  | 2015-03-30 | bill pay | 2000 |  |  |  | Original Contract: email 1/20/15
| Ahmann | [6 empty] | 22514.99 | 16500
| Currie & Associates | 1 | 300 | 2014-10-03 | bill pay | 300 |  |  | 300
| Currie & Associates | 1 | 850 | 2014-09-22 | 2106 | 850 |  |  | 850
| Geotech Engineers Soil Testing | 1 | 700 | 2015-06-26 | 2137 | 700 |  |  | 700 | original invoice in email 3/26/15
| Geotech Engineers Soil Testing | 1 | 700 | 2015-04-03 | 2129 | 700 |  |  | 700 | invoice in email 6/11/15
| Lourenco inspections | 4 | 200 | 2016-06-30 | HELOC bill pay | 800 |  |  | 3000 | http://dcra.dc.gov/node/514182
| GEICO all risks insurance | 1 | 1418.14 | 2015-12-11 | HELOC cc | 1418.14 |  |  | 1418.14 | Expires 6/12/2016
| GEICO all risks insurance | 1 | 874 | 2016-05-23 | HELOC 114 | 874 |  |  | 874 | Expires 12/12/2016
| Appliances diagnoses | 1 | 100 | 2015-12-30 | HELOC 101 | 100 |  |  | 100 | Appliance Services Inc, 202-409-6056 Dishwasher not fixable, stove needs spark module and 3 switches ($255-50), fridge needs water valve ($269-25)
| Datumeast Inc. Wall Check Surveyor |  |  | 2016-04-18 | bill pay | 700
| Misc | [6 empty] | 6442.14
Pre 2: | Solar
Budget
6877.5 | Solar Solution |  |  | 2015-04-27 | 2133 | 2598.75 |  |  |  | Paper invoice
| Solar Solution |  |  | 2016-05-26 | HELOC 115 | 2598.75
| Solar Solution |  |  | 2016-06-13 | HELOC 117 | 6877.5
Actual | Solar Solution | [6 empty] | 12075 | 17325
12075 | Upfront SREC Credit | [7 empty] | -5250
| Solar Tax Credit | [7 empty] | -5197.5
Pre 3: | Miscellaneous
Budget
9400 | misc. tools | [7 empty] | 8000
Actual | trash - 10 pulls | 4 | 350 | [5 empty] | 1400
1 | General Requirements
Budget
2340
Actual
2340
| OMF Division 1: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 1170 | 1170
| OMF Division 1: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 1170 | 1170
[8 empty] | 2340 | 2340
2 | Demolition and Sitework
Budget
18240
Actual
18240
| OMF Division 2: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 10944 | 10944
| OMF Division 2: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 7296 | 7296
| OMF Division2: Return Deposit |  |  | 2015-12-17 | HELOC 8001 | -17400 | -17400 |  |  | http://www.vcs-va.com/
| OMF Division2: Deposit |  |  | 2015-12-17 | HELOC 8001 | 17400 | 17400
[8 empty] | 18240 | 18240
3 | Concrete
Budget
10916
Actual
10916
| OMF Division 3: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 10916 | 10916
[8 empty] | 10916 | 10916
4 | Masonry
Budget
27065
Actual
18465
| OMF Division 4: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 3573 | 3573
| OMF Division 4: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 14292 | 14292
| OMF demo kitchen wall and install support | [7 empty] | 3900
| OMF demo stairs | [7 empty] | 5300
| Josue Corado patch chimney |  |  | 2016-04-20 | cash | 600
[8 empty] | 18465 | 17865
5 | Metals
Budget
2341
Actual
0
OMF Division 5
[8 empty] | 0 | 2341
6 | Wood and Carpentry
Budget
78810
Actual
94572
| OMF Division 6: Invoice 22314 |  |  | 2016-05-05 | HELOC 112 | 15762 | 15000
| OMF Division 6: Invoice 22287 |  |  | 2016-05-05 | HELOC 112 | 15762 | 762
| OMF Division 6: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 31524 | 31524
| OMF Division 6: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 31524 | 31524
[8 empty] | 94572 | 78810
7 | Thermal and Moisture Protection
Budget
25128
Actual
32778
| OMF Division 6: Invoice 22287 |  |  | 2016-05-05 | HELOC 112 | 5025.6 | 5025.6
| OMF Division 6: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 20102.4 | 20102.4
| Novafoam: spray foam insulation | 1 | 7650 | 2016-08-12 | HELOC cc | 7650
[8 empty] | 32778 | 25128
8 | doors
Budget | 5 interior doors | 1
15360 | master bath new - 25"
Actual | Closet Doors
15360
interior doors
| OMF Division 8: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 15360 | 15360
[8 empty] | 15360 | 15360
9 | Finishes and Accessories
Budget
15080
Actual
23354.05
| OMF Division 9: Invoice 22287 |  |  | 2016-05-05 | HELOC 112 | 3000 | 3000
| Finishes and Accessories estimate from OMF | 0 | 15080 | [5 empty] | 0 | mygirlsflooring.com, 301-861-0220
| tile - Floor and Décor | 1 | 2772 |  |  | 2772 |  |  | 2772
| tile - Neighbor Bryan | 0 | 8 | [5 empty] | 0
| Décor Island shower | 1 | 717 | 2016-05-17 | HELOC cc | 717 |  |  | 1000 | $7/s.f. + $1/s.f. if include cement board
| Loudon Stair's stairs | 1 | 5380.48 | 2016-05-18 | HELOC cc | 2690.24 |  |  | 5380.48 |  | http://carderock.com/tristatestone.html
| Loudon Stair's railing | 1 | 5000 | 2016-06-06 | HELOC cc | 2774.81 |  |  | 5000
| Edil Zepeda | 1 | 7400 | 2016-07-11 | HELOC 119 | 4000 |  |  | 7400 | I don't think he gave me primer and 2 coats on the porch. I am suspicious about the rest.
| Edil Zepeda |  |  | 2016-07-27 | HELOC 120 | 3400 |  |  | 0
| Rigo Zaldana: Drywall, Paint, Tile, Trim | 1 | 16000 | 2016-08-15 | HELOC 123 | 4000 |  |  | 16000
| Capitol Building Supply: Drywall, cement board, etc | 1 | 2734.86 | 2016-08-16 | HELOC cc | 2734.86
23354.05
15 | Plumbing & Mechanical
Budget
42031.15
Actual
33424.8
| disconnect 2 AC units |  |  | 2015-12-11 | 2156 | 500 |  |  | 500 | 12/11: Allied Service Company
| ductwork: payment 1 | 1 | 4400 | 2016-02-09 | HELOC 106 | 1500 |  |  | 4400 | Allied Service Company, email agreement 2/8, $4400
| ductwork: payment 2 |  |  | 2016-04-14 | HELOC 111 | 2000
| reconnect 2 AC units | 1 | 3500 | 2016-06-05 | HELOC 116 | 3500 |  |  | 1000
| Air Conditioning | [6 empty] | 7500
| radiant floor heating | 0 | 13720 | [5 empty] | 0 | 12/18: Estimate from Dave Glick from Aspen Hill plumbing $13,720, not including warmboard
| install radiant floor heating: payment 1 | 1 | 2000 | 2016-04-05 | HELOC 110 | 1000 |  |  | 2000 | Allied Service Co. Bob Gable email agreement 3/25/16
| warmboard, estimate | 1000 | 7.79 | [5 empty] | 7790 | 1/4: Provided drawings and paid design fee $500 by HELOC credit card. Receipt by email.
| warmboard, deposit |  |  | 2016-01-04 | HELOC cc | 500
| warmboard, balance |  |  | 2016-04-22 | HELOC cc | 5848.8
| warmboard install, Frank | 11 | 30 | 2016-05-04 | cash | 330
| warmboard install, Frank | 12 | 25 | 2016-05-13 | cash | 300
| pex install, Frank | 12.5 | 25 | 2016-05-20 | cash | 312.5
| central heating materials | 1 | 1041.15 |  |  | 1041.15 |  |  | 1041.15 | 3/19: See warmboard sheet. Online purchases from supplyhouse and pexuniverse. Tubing, manifolds, mixing valve, circulating pump, and tools
| central heating materials | 1 | 88.9 | [6 empty] | Pex from basement to third floor manifold
| central heating materials | 1 | 76.39
| radiator heating | 0 | 23040 | [5 empty] | 0 | 12/18: Estimate from Dave Glick from Aspen Hill plumbing $23,040
| Combo boiler/hot water | 1 | 7000 | 2015-12-21 | 8000 | 1500 |  |  | 7000 | 12/16: Paid $1500 of $3000 to Bob Gable from Allied Service Co. for plumbing work in foundation outside basement exit. Change in plans. No work in foundation. Tie into stack at kitchen and basement. Offered Bob $300 for saving $3000 if things hold up. | http://www.supplyhouse.com/Triangle-Tube-CC-125-96000-BTU-Output-Challenger-Combo-Boiler-Space-Heating-Domestic-Hot-Water
| Combo boiler/hot water |  |  | 2016-01-11 | 103 | 6000 |  |  |  | Installed 1/7. Paper receipt
| Heating | [6 empty] | 16832.45
| toilets | 2 | 400 | [5 empty] | 800
| tub/shower | 1 | 500 | [5 empty] | 500
| Ferguson Enterprises, shower valves | 2 | 82.285 | 2016-08-19 | HELOC cc | 164.57
| bathroom sink (3) and shower (2) faucets | 1 | 927.78 | 2016-08-13 | Amazon cc | 927.78
| sink | 3 | 1000 | [5 empty] | 3000
| new tub | 2 | 1000 | [5 empty] | 2000
| service, drains, vents | 0 | 25750 | [5 empty] | 0 | 12/18: Estimate from Dave Glick at Aspen Hill Plumbing
| service, drains, vents: payment 1 | 1 | 12000 | 2016-04-14 | HELOC 111 | 3000 |  |  | 12000 | 1/3: Bid from Bob Gable Allied Service Co.
| payment 2 |  |  | 2016-08-09 | HELOC 122 | 5000
| recirculating hot water | 0 | 1850 | [5 empty] | 0 | 12/18: Estimate from Dave Glick at Aspen Hill Plumbing
| Plumbing for bathrooms | [6 empty] | 9092.35
16 | Electrical
Budget
22600 | Lights, estimate | 1 | 4000 | [5 empty] | 4000
Actual | Rudy Lopez | 1 | 14900 | 2016-01-05 | HELOC 102 | 7450 |  |  | 14900
15676.84 | Rudy Lopez | 1 | 1000 | 2016-01-15 | HELOC 104 | 1000 |  |  | 1000
| Rudy Lopez | 1 | 3000 | 2016-05-05 | HELOC 113 | 3000
| Lights, Dominion Electric | 1 | 1057.54 | 2016-04-29 | HELOC cc | 1057.54
| Lights, Houzz | 2 | 129.2 | 2016-04-29 | HELOC cc | 258.4
| Bulbs | 1 | 210.9 | 2016-04-27 | HELOC cc | 210.9
| Merrick Campbell Estimate | 0 | 22600 | [5 empty] | 0
| misc. elec | 1 | 2700 |  |  | 2700 |  |  | 2700 | 3/23/13: Joel Cruz
Pepco builders and inspectors Ken Murray: 202-331-6237, (fax 202-388-2721)
| Electrical | [6 empty] | 15676.84
MISC | MISC
Budget
0
Actual
16141.14
| Change Order 3, Staircase 2nd and 3rd floor repairs and wall between kitchen and sunroom lintel |  |  | 2016-05-05 | HELOC 112 | 9200 | 9200
| payment change orders 1 and 2 |  |  | 2016-05-05 | HELOC 112 | 3800 | 2500
| Change Order 1, CMU walls at corners of 3rd floor: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 1200 | 1200
| Change Order 2, synthetic slate: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 1300 | 1300
| Mario Lemus demo ceiling bedroom and bath |  |  | 2016-04-20 | cash | 250
| Frank repair neighbors wall | 3 | 25 | 2016-05-26 | cash | 75
| Frank build wall master bath | 3 | 25 | 2016-06-25 | cash | 75
| Tools | 1 | 21.14 | 2016-01-09 | cc | 21.14
| Appliance Diagnostics | 1 | 100 | 2016-01-11 | 101 | 100
| Misc labor: demo and clean | 4 | 30 | 2016-03-12 | cash | 120
| Home Depot | 1 | 143.35 | 2016-04-24 | HELOC cc | 143.35
| Home Depot | 1 | 68.47 | 2016-05-02 | HELOC cc | 68.47
| Home Depot | 1 | 128.73 | 2016-05-08 | HELOC cc | 128.73
| Misc | [6 empty] | 16141.14
| Total budget |  |  |  |  | 335792.4 | 185859 |  | 332953.27

## cash
Accounts | Updated 7/26/2015
| balance | rate | monthly payment
refinance | 121286.96
Schwab Brokerage | 28561
equity line | 67000 | 3% | 0.25% below prime
TSP loan | 50000 | 2.125% | 812
total liquid |  |  |  | 266847.96
prosper | 35383 |  |  | Stopped reinvesting on 7/7/15. Cash balance $3000 on 8/23. Cash available is $2000 per month
Schwab Inh IRA | 138629
Schwab Roth | 111367
TSP | 260000
FERS
total total |  |  |  | 812226.96
Debt | Updated 7/26/2015
| balance | rate | monthly payment
Mortgage | 405000 | 3.85% | 2632 | I can offset this (increase) by taking distributions from my Prosper account.
HELOC | 67000 | ?3.85? | 500 | I can offset this by taking distributions from my Prosper account.
TSP loan | 50000 | 2.125% | 812 | I can offset this by reducing TSP constributions (currently $660)
E: Student Loan | 30000 | 3% | 260
E: Car Loan | 23600 | 1.5% | 593
total | 575600 |  | 4797 | 575600
Income Retirement | Updated 7/26/2015
| balance | rate | monthly payment
TSP | 260000 |  | 1329 | $4800/month projected monthly payment assuming continued savings
Social Security |  |  | 2403 | Assuming work until 67. At 62 can receive $1566/month.
FERS |  |  | 2475 | Assuming work until 65. At 62 can receive 2235/month.
Charles Schwab Retirement Planning Calculator |  |  | https://client.schwab.com/Areas/Accounts/RetirementAssessment/YourInfo.aspx
Retirement age | 65
Life Expectancy | 90
Current salary | 134662
effective tax rate from paystub | 22.28%
Tax-advantaged retirement savings | 509996 |  | Includes TSP, Roth, and Schwab Inh IRA. Does not include FERS
Total amount you/your employer contribute annually | 29160 |  | From paystub (me+gov+gov) and IRA contribution
Taxable savings intended for retirement | 63944 |  | Includes prosper and brokerage
Yearly taxable savings for retirement | 0
Moderate-aggressive pre-retirement
Moderate-conservative after retirement
% current income, retirement spending |  | 100%
Soc Sec Ben |  |  | Calculate automatically. Begin receiving at 67
Retirement income | 0
Retirement Savings Projected | Report 7/26/2015 |  |  | 1720237
Retirement Savings Needed |  |  |  | 1380871
Surplus Retirement |  |  |  | 339366
Project Size
first | 1038 | 39400% | sf
second | 825 | 49000% | sf
total existing | 1863 | 88400% | sf
TOTAL BUILDING | 2747
$500/sf | 1373500

## WaterTight
Building Envelope
2015-07-25 | scheule for windows and doors sent and estimate requested
| steve | 84 LUMBER CO. #0913: | 5321 MARLBORO PIKE, UPPER MARLBORO, MD 20772 (17.36 mi) | 301-952-0584 | marinos@0913.84lumber.com
|  | LAMAR & WALLACE, INC. | 7000 OLD LANDOVER ROAD LANDOVER,MD 20785-1504 | 301-772-2400
|  | GALLIHER & HUGUELY ASSOCIATES, INC. | 5925 BLAIR RD. NW WASHINGTON,DC 20011-2343 | 202-723-1000
[12 empty] | total | 5.75% tax
| Windows |  | Jeld-Wen quote from Galliher & Hugueley | 5434.2176 | [7 empty] | 5138.74 | 295.4776
|  |  |  | Required | Provided |  |  | Need sash limiters
|  | Plans Pg A-0 | Energy Conservation | U-Factor = 0.35 | TBD |  |  | Quote based on 4-9/16" jambs.
|  | Plans Pg A-4 | Window and Exterior Door Schedule |  |  |  |  | what are the jamb sizes?
Floor | Room | ID in plans | Description and model from architect | Description and model from owner | Description and model from supplier | Planned width | Planned Height | Rough opening width | Rough opening height | # items | cost per item | total cost | delivery time
Third Floor | Bedroom | 1 | Jeld-Wen 2-3756 with 5-1/2" mull: Double Hung Window | Jeld-Wen: W-2500, Two Double Hung windows with 5.5" mull. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 78" | 54" | 76.25" | 56.75" | 1 | 740.75 | 740.75 | 3-4 weeks | s0122 | s0127 | Line 6 | mulled together
First Floor | Sun Room | 2.A1 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, Two mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" | 40.75" | 54.75" | 2 | 599.66 | 1199.32 | 3-4 weeks | s0106 | s0114 | Line 3
First Floor | Sun Room | 2.A2 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" |  |  | 0 |  | 0 | 3-4 weeks
First Floor | Sun Room | 2.A3 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, Two mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 96" |  |  | 0 |  | 0 | 3-4 weeks
First Floor | Sun Room | 2.A4 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 42" | 96" |  |  | 0 |  | 0 | 3-4 weeks
Second Floor | Master Bath | 2.B | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, 2 mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" | 40.75" | 54.75" | 3 | 599.66 | 1798.98 | 3-4 weeks | s0145 | s0152 | Line 5
First Floor | Sun Room | 3 | Jeld-Wen 1754 fixed | Jeld-Wen: W-2500, one casement window, fixed, no grille, white | Jeld-Wen: see quote | 12" to 18" | 60" | 20.75" | 54.75" | 2 | 254.9 | 509.8 | 3-4 weeks | s0101 | s0105 | Line 1, Line 2
First Floor | Sun Room | 3 | Jeld-Wen 1754 fixed | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 12" to 18" | 60" |  |  | 0 |  | 0 | 3-4 weeks
Third Floor | Bedroom | 4.A | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks | s0128 | s0133 | Line 7
Third Floor | Recreation room | 4.B | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks | s0128 | s0133 | Line 7
Third Floor | Bathroom | 4.C | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks | s0153 | s0155
[12 empty] | total | 5.75% tax
| Doors |  | Lemieux, Masonite quote from Galliher & Hugueley | 2526.3675 | [7 empty] | 2389 | 137.3675
|  |  |  | Required | Provided |  |  | Can I remove T-astragal?
|  | Plans Pg A-0 | Energy Conservation | U-Factor = 0.35 | TBD |  |  | Quote based on 4-9/16" jambs.
what are the jamb sizes?
|  | Plans Pg A-4 | Window and Exterior Door Schedule
Floor | Room | ID in plans | Description and model from architect | Description and model from owner | Description and model from supplier | Planned width | Planned height | Width from supplier | Height from supplier | # items | cost per item | total cost | delivery time
Basement | Exit | A | Basement panel door with glass | Smooth-pro fiberglass panel exterior door, 1/2 view 9-light, 1-panel, screened | Masonite BLS-106-09I | 3' | 6'-8" | 3' | 6'-8" | 0 | 442 | 0 | 4-6 weeks
Basement | Exit | A.alternate | Basement panel door with glass | Authentic wood glass panel exterior door 5209 | Lemieux F5944 | 3' | 6'-8" | 3' | 6'-8" | 1 | 650 | 650 | 4-6 weeks
First Floor | Sun Room | B | Hinged patio door (inswing) Transom (3'x1') mulled above | Door from existing 2nd fl bedroom exit Security storm door from existing kitchen exit Transom (2'-6" x 1'-4") mulled above | Does current door with security storm door pass U-Factor? | 2'-6" | 6'-8" | 2'-6" | 6'-8" | 1 | 0 | 0 | EXISTING
First Floor | Sun Room | B.alternate | Hinged patio door (inswing) Transom (3'x1') mulled above | Hinged patio door (inswing) Transom (3'x1') mulled above | Lemieux 5001 W/Transom | 3' | 7' | 3' | 7' | 0 | 698 | 0 | 1-2 weeks
Third Floor | Exit To Balcony | C | Hinged patio door (inswing, 2-panel) | Authentic wood glass panel exterior door 5001 | Lemieux 5001 W/T-astragal | 6' | 6'-8" | 6' | 6'-8" | 1 | 949 | 949 | 1-2 weeks
Basement | Outside Under Sun Room | D | Paneled storage doors (inswing) | Smooth-pro fiberglass panel exterior door, 2-panel square top (match other basement door, no window) | Masonite 2-panel smooth fiberglass with T-astragal and slide bolt Can I remove the T-astragal? | 5' | 6'-8" | 5' | 6'-8" | 1 | 790 | 790 | 4-6 weeks
Roofs/Ceilings
Floor | Room | ID in plans | Desc | Detailed Description | Source and delivery |  |  | Width nominal (ft) | Height nominal (ft) | total (sf) | cost per sf: materials, supplies, tools |  | cost total
Estimates from | http://www.homewyse.com/
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | R-38 OR R-38C (10 1/4" HIGH DENSITY BATT) AT ATTIC AS ALLOWED BY EXISTING CLEARANCE, 2X8 rafters |  |  |  | 20 | 36 | 720 | 1.15 |  | 828
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | R-38 OR R-38C (10 1/4" HIGH DENSITY BATT) AT ATTIC AS ALLOWED BY EXISTING CLEARANCE, 2X8 rafters |  |  |  | 9 | 76 | 684 | 1.15 |  | 786.6
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | 6 1/2" CLOSED CELL SPRAY FOAM (R38) ABOVE TOP PLATES AT EAVE, 2X8 rafters @ eaves |  |  |  | 8 | 16 | 128 | 1.15 |  | 147.2
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 20 | 36 | 720 | 3 |  | 2160 | homewyse says $3/sf for materials, tools, supplies
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 9 | 76 | 684 | 3 |  | 2052
Second floor | Flat roof | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 8 | 16 | 128 | 3 |  | 384
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Fiberglass shingles |  |  |  |  | 9 | 76 | 684 | 3 |  | 2052
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 20 | 36 | 720 | 0.5 |  | 360
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 9 | 76 | 684 | 0.5 |  | 342
Second floor | Flat roof | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 8 | 16 | 128 | 0.5 |  | 64
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Balcony floor | Duradek walkable floor membrane |  |  |  | 8 | 16 | 128 | 10.5 |  | 1344
Walls (Wood Framing)
|  |  |  | Required | Provided
|  |  | Energy Conservation | R-Value = R-20 or R-13+5 | R-21, 2X6 frame walls
Mass Walls
|  | Plans Pg A-0 | Energy Conservation, Required R-Value = R-8/13
Second floor | Master Bath | Plans Pg A-5
Basement Walls
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10/13 | N/A
Floors
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-19 | R-Value = R-30, 2X10 floor joists
Slab Perimeter R-value and Depth
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10, 2FT depth | N/A
Crawl Space
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10/13 | N/A
Infiltration
ALL EXTERIOR JOINTS SHALL HAVE A HIGH QUALITY DETAILED, AIR SEALING APPLIED TO INCLUDE BUT NOT LIMITED TO PICTURE FRAMING STUDS, BOTTOM PLATES, TOP PLATES, AROUND WINDOWS AND DOORS, EXHAUST PENETRATIONS, WIRING PENETRATIONS OSB GAPS, RIM JOISTS, AND NAIL-HOLES

## Flores
Original Bid |  | Water-tight Bid
1. DIVISION 1: General requirements | 17000 | 17000
2. DIVISION 2: Demolition and sitework | 15025 | 15025
3. DIVISION 3: Concrete | 8500 | 8500
4. DIVISION 4: Masonry | 13125 | 13125
5. DIVISION 5: Metals | 1800
6. DIVISION 6: Wood/ Carpentry | 65075 | 65075
7. DIVISION 7: Thermal and moister protection | 19840 | 19840 | This is an overestimate because it does not include insulation.
8. DIVISION 8: Doors and windows | 14300 | 14300
9. DIVISION 9: Finishes and accessories | 15080
10. DIVISION 10 -14: Not included | 0
11. DIVISION 15: Plumbing and Mechanical | 32000 | 1000 | This is an uneducated guess.
12. DIVISION 16: Electrical | 15500
13. ALLOWANCES: | 10240
 Ceramic tile – 360 Sf @ $ 7.50 p/Sf = $ 2,700.00 |  | 0
 Counter top slab – 16 Sft @ $ 65.00 = $ 1,040.00 |  | 0
 Plumbing fixtures and bath accessories - $ 5,000.00 |  | 0
 Bath vanities for powder room and master bath - $ 1,500.00 |  | 0
0
TOTAL | 227485 | 153865
14. OVERHEAD AND PROFIT- 20% | 45497 | 30773
Compare to
GRAND TOTAL | 272982 | 184638 | 174000

## warmboard
Approved tubing list at the bottom
PEX Tubing Calculator
1. What is the total square footage of the area you want to cover? | [6 empty] | 1000 Sq. Ft.
2. How many inches apart will the loops be spaced? Learn More | [6 empty] | 8 inches
You will need 1,500 ft of oxygen barrier PEX tubing. | [6 empty] | 1500 Ft
http://www.moen.com/connection-types | Plumbing connections |  |  | IPS is a threaded connection type.
http://www.supplyhouse.com/resources/pexConnections | Pex compression fitting Connections |  |  | Compression fittings may be used to make connections for PEX and PEX-AL-PEX tubing. Compression fittings do not require a special tool.
http://s3.supplyhouse.com/product_files/Uponor-A6140750-sizing-guide.pdf | Pipe sizing guide
TUBING | location |  |  |  | URL | supplier | Qty Ft | total cost
1/2" hePEX - (500 ft. coil) SKU:A1260500 Brand: Uponor (Wirsbo) | in boards |  |  |  | http://www.supplyhouse.com/Wirsbo-Uponor-A1260500-1-2-hePEX-plus-500-ft-coil | supply house | 1500 | 844.85 | 5 stars | 73 reviews
1/2" PEX-AL-PEX Tubing (1,000 ft Coil) SKU:050-1000-PAP Brand: Rifeng | in boards |  |  |  | http://www.supplyhouse.com/Rifeng-050-1000-PAP-1-2-PEX-AL-PEX-Tubing-1000-ft-Coil | supply house | 1500 | 561.85 | 5 stars | 17 reviews
1/2" x 1000ft PEX-AL-PEX Tubing Everhot Brand: Everhot Mfr Part#: APX1210 | in boards |  |  |  | http://www.pexuniverse.com/apx1210-1-2-x-1000ft-pex-al-pex-tubing | pexuniverse | 1500 | 506.9 | unrated
3/4" Pre-Insulated Wirsbo hePEX w/ 1/2" Insulation, 100 ft coil SKU:A6140750, Brand: Uponor (Wirsbo) | to/from manifold |  |  |  | http://www.supplyhouse.com/Uponor-Wirsbo-A6140750-3-4-Pre-Insulated-Wirsbo-hePEX-w-1-2-Insulation-100-ft-coil | supply house | 100 | 269.95
7/8" Pipe (O.D.) x 1/2" Wall Insul-Lock Pipe Insulation, 6' | for 3/4" copper pipe to/from basement and 3rd floor |  |  |  | http://www.supplyhouse.com/K-Flex-6RXL048078-7-8-Pipe-OD-x-1-2-Wall-Insul-Lock-Pipe-Insulation-6 | supply house | 40 | 52.3333
Manifolds | location | supply return type | pex type |  | URL | supplier |  | total cost
3 Loop Stainless Steel Manifold Package - 1/2" PEX-AL-PEX | 3rd floor | 1", BSP | 1/2" |  | http://www.supplyhouse.com/Rifeng-RHM03-50PAPK-3-Loop-Stainless-Steel-Manifold-Package-1-2-PEX-AL-PEX |  |  | 138.95
3-branch Stainless Steel Radiant Heat Manifold Set w/ 1/2" PEX adapters Brand: Rifeng Mfr Part#: SSM103 | 3rd floor | 1" IPS (iron pipe straight) threaded ball valve | 1/2" 5/8" adapters available | Pex compression-style adapters | http://www.pexuniverse.com/ssm103-steel-radiant-heat-manifold |  |  | 122.95 |  | On user guide: What is G1" connection?
2-branch Stainless Steel Radiant Heat Manifold Set w/ 1/2" PEX adapters, Brand: Rifeng, Mfr Part#: SSM102 | basement | 1" NPT (national pipe tapered) threaded ball valve |  | Pex compression-style adapters | http://www.pexuniverse.com/ssm102-steel-radiant-heat-manifold |  |  | 101.95
3 Loop Stainless Steel PEX Manifold with 1/2" Connectors w/ Automatic Purge Valve | 3rd fl and basement | 1" NPT threaded ball valve | 1/2" 5/8" adapters available |  | http://www.pexsuperstore.com/pex-manifolds/radiant-pex-manifolds/connectors/3-loop-stainless-steel-pex-manifold-with-1-2-inch-connectors.html |  |  | 122.95
3-Loop 1" Stainless Steel Radiant Heat Manifold Assembly w/ Flow Meter SKU:A2700302 Brand: Uponor (Wirsbo) | 3rd fl and basement | 1" NPT threaded ball valve | 1/2" 5/8" requies 6 loop fitting assemblies | PEX compression, PEX-AL-PEX compression | http://www.supplyhouse.com/Uponor-Wirsbo-A2700302-3-Loop-1-Stainless-Steel-Radiant-Heat-Manifold-Assembly-w-Flow-Meter |  |  | 219.95
Mixing Valve | location | supply return type | pex type |  | URL | supplier |  | total cost
1/2" PEX Union 5002 Heating Only Mixing Valve
1/2" NPT Mixing Valve, Lead Free (70°F-145°F), SKU:AM100-1LF |  |  |  | requires adaptor below | http://www.supplyhouse.com/Honeywell-Sparco-AM100-1LF-1-2-NPT-Mixing-Valve-Lead-Free-70176F-145176F |  |  | 80.95
1/2" PEX-AL-PEX Compression x 1/2" Male Threaded Adapter, SKU:PAP-0500M |  |  |  | adaptor | http://www.supplyhouse.com/Rifeng-PAP-0500M-1-2-PEX-AL-PEX-Compression-x-1-2-Male-Threaded-Adapter |  |  | 2.56
1" Thermostatic Mixing Valve 80 to 165°F, Lead Free (Union Sweat) |  |  |  |  | http://www.supplyhouse.com/Zurn-1-ZW1017XLHTC-1-Thermostatic-Mixing-Valve-80-to-165F-Lead-Free-Union-Sweat |  |  | 139.95
Circulating pump | location | supply return type | pex type |  | URL | supplier |  | total cost
Requirements:
Star S 21F, 3-Speed Cast Iron Star Series Circulator, 1/12 HP, SKU:4105032, Brand: Wilo |  |  |  |  | http://www.supplyhouse.com/Wilo-4105032-Star-S-21F-3-Speed-Cast-Iron-Star-Series-Circulator-1-12-HP |  |  | 75.95
Misc | location | supply return type | pex type |  | URL | supplier |  | total cost
PEX-al-PEX Chamfering Tool (1/2", 3/4", 1"), SKU:8220875, Brand: Mr. PEX |  |  |  |  | http://www.supplyhouse.com/Mr-PEX-8220875-PEX-al-PEX-Chamfering-Tool-1-2-3-4-1 |  |  | 18.55
Tube Cutter, (plastic) up to 1" PEX, SKU:E6081128, Brand: Uponor (Wirsbo) |  |  |  |  | http://www.supplyhouse.com/Wirsbo-Uponor-E6081128-Tube-Cutter-plastic-up-to-1-PEX-2165000-p |  |  | 19.95
1041.15
Approved tubing list 4
Pex Aluminum Pex tubing 1/2" ID
y AIM: Pex AL Pex
y Allied Pipe Systems: Pex AL Pex
y Aqua Therm: Pex AL Pex
y ComfortPro: Pex AL Pex
y EHT (Efficient Heating Technology): Pex AL Pex
y Everhot: Pex AL Pex
y Excel: Pex AL Pex
y Henco: Pex AL Pex
y Hydro-flex: Pex AL Pex
y HYDRONX: Pex AL Pex
y Inferno: Pex AL Pex
y Infloor Heating Systems: Pex AL Pex
y Mr. Pex: Pex AL Pex
y RHT: Pex AL Pex
y Rifeng: Pex AL Pex
y Roth: Pex AL Pex
y Uponor: Multi-Layer composite tubing (MLC)
Pex AL Pex
y Watts: Pex AL Pex
y Weil-McLain: Pex AL Pex
y WSD (Willow Springs Distributing) Pex AL Pex
y Zurn Alumicor: Pex AL Pex
Standard Barrier Pex 1/2" tubing ID
y Mr. Pex (LK Pex AB)
y Rehau Raupex Oxygen barrier manufactured after
3/8/11-date printed on tubing
y ThermaPEX (LK PEX)
y Uponor Wirsbo hePEX
y ViegaPEX Barrier
y Watts RadiantPEX+

## Staircase
Loudoun Stairs / 540-338-7400
Century Stair Company / 703-753-3912
Southern Staircase / 800-874-8408

## electrical
ID from BDG in red | ID from plans | Item | Purchased | Provided by | Floor | Location
1 | n/a | WATER PROOF DUPLEX OUTLET | n/a | Electrician | 3 | Balcony | X
2 | 6 | EXTERIOR SCONCE | No | Homeowner | 3 | Balcony | X
3 | 6 | EXTERIOR SCONCE | Delete | Homeowner | 3 | Balcony | Delete
4 | n/a | WATER PROOF DUPLEX OUTLET | n/a | Electrician | 3 | Balcony | X
5 | 6 | EXTERIOR SCONCE | Delete | Homeowner | 3 | Balcony | Delete
6 | n/a | DIMMER SWITCH | n/a | Electrician | 3 | Balcony | X - top of stairs
7 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room at Balcony exit North | X
8 | 5 | INTERIOR SCONCE | Yes | Homeowner | 3 | Bathroom | wire - wait for finish
9 | n/a | DUPLEX OUTLET WITH GROUND FAULT CIRCUIT PROTECTION | n/a | Electrician | 3 | Bathroom | X
10 | n/a | DIMMER SWITCH | n/a | Electrician | 3 | Bathroom | X
11 | n/a | SWITCH | n/a | Electrician | 3 | Bathroom | X
12 | n/a | DIMMER SWITCH | n/a | Electrician | 3 | Bathroom | X
13 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Bathroom | X
14 | 2 | RECESSED 5" DOWNLIGHT, WET LOCATION: PHILIPS LIGHTOLIER LYTECASTER 5" APERTURE RECESSED DOWNLIGHT FLUSH GLASS WET LOCATION TRIM, #1090 REFLECTOR, #1002P1 75W PAR30L NON-‐IC OR #1000IC 60W PAR30S IC, PROVIDE MAX. ALL. LAMPS (TYP) | Delete ? | Homeowner | 3 | Bathroom | Delete ?
15 | V | Fan + light | Yes | Homeowner | 3 | Bathroom NOTE: VENT FANS TO BE ON TIMERS WITH AUTO SHUT-OFF | X - move above tub, fan goes on timer
16 | 2 | RECESSED 5" DOWNLIGHT, WET LOCATION: PHILIPS LIGHTOLIER LYTECASTER 5" APERTURE RECESSED DOWNLIGHT FLUSH GLASS WET LOCATION TRIM, #1090 REFLECTOR, #1002P1 75W PAR30L NON-‐IC OR #1000IC 60W PAR30S IC, PROVIDE MAX. ALL. LAMPS (TYP) | Delete | Homeowner | 3 | Bathroom | Delete
17 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room north wall | X
18 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room north wall | X
19 | n/a | CABLE CONNECTION | Yes | Homeowner | 3 | Recreation room east wall | Brandon ran wire
20 | n/a | DUAL TEL/ETHERNET JACK | Yes | Homeowner | 3 | Recreation room east wall | Brandon ran wire
21 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room east wall | X
22 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room east wall | missing, remove 1 gang box (item 21) before dry wall, expose wire after drywall for "old-work" 2 gang box (four outlets)
22B | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room east wall | NEW addition, remove 1 gang box before dry wall, expose wire after drywall for "old-work" 2 gang box
23 | n/a | CABLE CONNECTION | Yes | Homeowner | 3 | Recreation room east wall | Brandon ran wire
24 | n/a | DUAL TEL/ETHERNET JACK | Yes | Homeowner | 3 | Recreation room east wall | Brandon ran wire
25 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room east wall | X
26 | n/a | CABLE CONNECTION | Yes | Homeowner | 3 | Recreation room south wall | Delete
27 | n/a | DUAL TEL/ETHERNET JACK | Yes | Homeowner | 3 | Recreation room south wall | Delete
28 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room south wall | X
29 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | Recreation room bathroom wall | X
30 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | 3rd Fl bedroom south wall | X
31 | n/a | CABLE CONNECTION | Yes | Homeowner | 3 | 3rd Fl bedroom west wall | Brandon ran wire
32 | n/a | DUAL TEL/ETHERNET JACK | Yes | Homeowner | 3 | 3rd Fl bedroom west wall | Brandon ran wire
33 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | 3rd Fl bedroom west wall | X
34 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | 3rd Fl bedroom north wall | X
35 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | 3rd Fl bedroom east wall | X
36 | n/a | CABLE CONNECTION | Yes | Homeowner | 3 | 3rd Fl bedroom east wall | Delete
37 | n/a | DUAL TEL/ETHERNET JACK | Yes | Homeowner | 3 | 3rd Fl bedroom east wall | Delete
38 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 3 | 3rd Fl bedroom east wall | X
39 | 4 | CLOSET LENSED LIGHT, PHILIPS ARIS LED, LOW PROFILE TASK LIGHT, 21" | No | Homeowner | 3 | 3rd Fl closet 1 | X
40 | 4 | CLOSET LENSED LIGHT, PHILIPS ARIS LED, LOW PROFILE TASK LIGHT, 21" | No | Homeowner | 3 | 3rd Fl closet 2 | X
41 | n/a | DIMMER SWITCH | n/a | Electrician | 3 | Outside 3rd Fl closet 1 | X
42 | n/a | DIMMER SWITCH | n/a | Electrician | 3 | Outside 3rd Fl closet 2 | X
43 | 1 | RECESSED 5" DOWNLIGHT, BASIC: PHILIPS LIGHTOLIER LYTECASTER 5" APERTURE STEP BAFFLE # 1005WH MATTE WHITE STEP BAFFLE REFLECTOR, #1002P1 75W NON-IC OR #100IC 75W PAR 30 IC, PROVIDE MAX. ALL LAMPS | Yes | Homeowner | 3 | 3rd Fl bedroom ceiling | X
44 | 1 | same as above | Yes | Homeowner | 3 | 3rd Fl bedroom ceiling | X
45 | 1 | same as above | Yes | Homeowner | 3 | 3rd Fl bedroom ceiling | X
46 | 1 | same as above | Yes | Homeowner | 3 | 3rd Fl bedroom ceiling | X
47 | n/a | SMOKE DETECTOR | n/a | Electrician | 3 | 3rd Fl bedroom ceiling | X
48 | n/a | DIMMER SWITCH | n/a | Electrician | 3 | 3rd Fl bedroom next to door | X
49 | n/a | CARBON DIOXIDE DETECTOR | n/a | Electrician | 3 | 3rd Fl recreation room ceiling | X
50 | n/a | SMOKE DETECTOR | n/a | Electrician | 3 | 3rd Fl bedroom ceiling | X
51 | n/a | SWITCH (3WAY) | n/a | Electrician | 3 | 3rd Fl bedroom next to door | X
52 | 1 | RECESSED 5" DOWNLIGHT, BASIC: PHILIPS LIGHTOLIER LYTECASTER 5" APERTURE STEP BAFFLE # 1005WH MATTE WHITE STEP BAFFLE REFLECTOR, #1002P1 75W NON-IC OR #100IC 75W PAR 30 IC, PROVIDE MAX. ALL LAMPS | Yes | Homeowner | 3 | 3rd Fl recreation room ceiling | X
53 | 1 | same as above | Yes | Homeowner | 3 | 3rd Fl recreation room ceiling | X
54 | 1 | same as above | Yes | Homeowner | 3 | 3rd Fl recreation room ceiling | X
55 | 1 | same as above | Yes | Homeowner | 3 | 3rd Fl recreation room ceiling | X
56 | n/a | DIMMER SWITCH (3 way) | n/a | Electrician | 3 | 3rd Fl bedroom next to door | X
57 | n/a | SWITCH (3WAY) | n/a | Electrician | 3 | 3rd Fl bedroom next to door | X
58 | 5 | INTERIOR SCONCE TO BE PROVIDED BY OWNER & INSTALLED BY CONTRACTOR | No | Homeowner | 3 | 3rd Fl recreation room between stairs and balcony exit | X
59 | 5 | same as above | No | Homeowner | 3 | 3rd Fl recreation room on bathroom wall | X
60 | 5 | same as above | No | Homeowner | 3 | 3rd Fl recreation room top of stairs | X
61 | 1 | RECESSED 5" DOWNLIGHT, BASIC: PHILIPS LIGHTOLIER LYTECASTER 5" APERTURE STEP BAFFLE # 1005WH MATTE WHITE STEP BAFFLE REFLECTOR, #1002P1 75W NON-IC OR #100IC 75W PAR 30 IC, PROVIDE MAX. ALL LAMPS | Yes | Homeowner | 3 | 3rd Fl recreation room ceiling over stairs | X
62 | n/a | DIMMER SWITCH (3 way) | n/a | Electrician | 3 | 3rd Fl bedroom next to door | X
63 | n/a | SWITCH (3WAY) | n/a | Electrician | 2 | 2nd Fl bottom of stairs | X
64 | 3 | SURFACE MOUNT FIXTURE LIGHTING FIXTURE TO BE PROVIDED BY OWNER & INSTALLED BY CONTRACTOR | n/a | Electrician | 2 | 2nd Fl hallway | X
65 | 3 | SURFACE MOUNT FIXTURE LIGHTING FIXTURE TO BE PROVIDED BY OWNER & INSTALLED BY CONTRACTOR | n/a | Electrician | 2 | 2nd Fl hallway | X
66 | 3 | SURFACE MOUNT FIXTURE LIGHTING FIXTURE TO BE PROVIDED BY OWNER & INSTALLED BY CONTRACTOR | n/a | Electrician | 2 | 2nd Fl hallway | X
67 | n/a | DIMMER SWITCH (3 way) | n/a | Electrician | 2 | 2nd Fl hallway | missing from bottom of stairs
68 | n/a | SMOKE DETECTOR | n/a | Electrician | 2 | 2nd Fl Master bedroom | X
69 | n/a | SMOKE DETECTOR | n/a | Electrician | 2 | 2nd Fl Boys bedroom | X
70 | n/a | SMOKE DETECTOR | n/a | Electrician | 2 | 2nd Fl Hallway | X
71 | n/a | CARBON DIOXIDE DETECTOR | n/a | Electrician | 2 | 2nd Fl Hallway | X
72 | n/a | SMOKE DETECTOR | n/a | Electrician | 2 | 2nd Fl Office | X
73 | n/a | DIMMER SWITCH | n/a | Electrician | 2 | 2nd Fl Office | Currently mounted outside office. Move to inside office?
74 | 3 | SURFACE MOUNT FIXTURE LIGHTING FIXTURE TO BE PROVIDED BY OWNER & INSTALLED BY CONTRACTOR | n/a | Electrician | 2 | 2nd Fl Office | X
75 | n/a | DIMMER SWITCH | n/a | Electrician | 2 | 2nd Fl master bath south side of door jamb | X
76 | 1 | RECESSED 5" DOWNLIGHT, BASIC: PHILIPS LIGHTOLIER LYTECASTER 5" APERTURE STEP BAFFLE # 1005WH MATTE WHITE STEP BAFFLE REFLECTOR, #1002P1 75W NON-IC OR #100IC 75W PAR 30 IC, PROVIDE MAX. ALL LAMPS | Yes | Homeowner | 2 | 2nd Fl master bath ceiling | X
77 | 1 | same as above | Yes | Homeowner | 2 | 2nd Fl master bath ceiling | X
78 | 1 | same as above | Yes | Homeowner | 2 | 2nd Fl master bath ceiling | X
79 | 1 | same as above | Yes | Homeowner | 2 | 2nd Fl master bath ceiling | X
80 | n/a | DIMMER SWITCH | n/a | Electrician | 2 | 2nd Fl master bath south side of door jamb | X
81 | 5 | INTERIOR SCONCE TO BE PROVIDED BY OWNER & INSTALLED BY CONTRACTOR | No | Homeowner | 2 | 2nd Fl master bath above vanity | X
82 | 5 | same as above | No | Homeowner | 2 | 2nd Fl master bath above vanity | X
83 | n/a | SWITCH FOR FAN | n/a | Electrician | 2 | 2nd Fl master bath south side of door jamb | X
84 | V | PANASONIC WHISPER CEILING MOUNTED BATHROOM FAN | Yes | Homeowner | 2 | 2nd Fl master bath ceiling, NOTE: VENT FANS TO BE ON TIMERS WITH AUTO SHUT-OFF | X - move to shower, fan goes on timer
85 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 2 | 2nd Fl master bath south side of door jamb | X
86 | n/a | DUPLEX OUTLET WITH GROUND FAULT CIRCUIT PROTECTION | n/a | Electrician | 2 | 2nd Fl master bath above vanity | X
87 | n/a | DUPLEX OUTLET WITH GROUND FAULT CIRCUIT PROTECTION | n/a | Electrician | 2 | 2nd Fl master bath above vanity | X
88 | n/a | DIMMER SWITCH | n/a | Electrician | 2 | 2nd Fl master bath north side of door jamb | X
89 | 2 | RECESSED 5" DOWNLIGHT, WET LOCATION: PHILIPS LIGHTOLIER LYTECASTER 5" APERTURE RECESSED DOWNLIGHT FLUSH GLASS WET LOCATION TRIM, #1090 REFLECTOR, #1002P1 75W PAR30L NON-‐IC OR #1000IC 60W PAR30S IC, PROVIDE MAX. ALL. LAMPS (TYP) | Delete | Homeowner | 2 | 2nd Fl master bath in shower | Delete
90 | n/a | SWITCH | n/a | Electrician | 2 | 2nd Fl master bath north side of door jamb | X
91 | 7 | BROAN HEAT LAMP: BROAN #162 ONE BULB HEATER/FAN, 250W BR40 INFRARED BULB, 70 CFM, IC RATED | Delete | Homeowner | 2 | 2nd Fl master bath in shower | Delete
92 | n/a | DIMMER SWITCH (3 way) | n/a | Electrician | 1 | Sunroom near kitchen and near door | X
93 | 1 | RECESSED 5" DOWNLIGHT, BASIC: PHILIPS LIGHTOLIER LYTECASTER 5" APERTURE STEP BAFFLE # 1005WH MATTE WHITE STEP BAFFLE REFLECTOR, #1002P1 75W NON-IC OR #100IC 75W PAR 30 IC, PROVIDE MAX. ALL LAMPS | Yes | Homeowner | 1 | Sunroom ceiling | X
94 | 1 | same as above | Yes | Homeowner | 1 | Sunroom ceiling | X
95 | 1 | same as above | Yes | Homeowner | 1 | Sunroom ceiling | X
96 | 1 | same as above | Yes | Homeowner | 1 | Sunroom ceiling | X
97 | n/a | SWITCH FOR FAN | n/a | Electrician | 1 | Sunroom near kitchen | X
98 | n/a | Fan + light | No | Homeowner | 1 | Sunroom ceiling | X
99 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 1 | Sunroom south wall | X
100 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 1 | Sunroom south wall | missing
101 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 1 | Sunroom west wall | X
102 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 1 | Sunroom north wall | X
103 | n/a | DUPLEX WALL OUTLET | n/a | Electrician | 1 | Sunroom north wall | X
104 | n/a | SWITCH | n/a | Electrician | 1 | Sunroom near door | X
105 | 6 | EXTERIOR SCONCE | No | Homeowner | 1 | Exterior at door | X
106 | n/a | DUAL HEAD ADJUSTABLELIGHT WITH MOTION SENSOR: PROGRESS #P5203-30 WITH TWO 100 WATT PAR38 LAMPS | No | Homeowner | 1 | Exterior west wall | X
107 | n/a | same as above | No | Homeowner | 1 | Exterior west wall | X
108 | n/a | DIMMER SWITCH | n/a | Electrician | 0 | Interior at exit | X
109 | 6 | EXTERIOR SCONCE | No | Homeowner | 0 | Exterior at exit | X
110 | n/a | DIMMER SWITCH | n/a | Electrician | 0 | Exterior next to closet | X
111 | 3 | SURFACE MOUNT FIXTURE LIGHTING FIXTURE TO BE PROVIDED BY OWNER & INSTALLED BY CONTRACTOR | n/a | Electrician | 0 | In closet | X
112 | n/a | WATER PROOF DUPLEX OUTLET | n/a | Electrician | 0 | In closet | X
113 | n/a | WATER PROOF DUPLEX OUTLET | n/a | Electrician | 0 | Outside closet | X
114 | 8 | EXTERIOR RECESSED ACCENT LIGHTING: PHILIPS LIGHTOLIER GARDCO 111 MINI SCONCE LED 111L-DIM, TYPE II | No | Homeowner | 0 | At steps | X
115 | 8 | EXTERIOR RECESSED ACCENT LIGHTING: PHILIPS LIGHTOLIER GARDCO 111 MINI SCONCE LED 111L-DIM, TYPE II | No | Homeowner | 0 | At steps | X

## shower
Plywood sheathing | 21/32 | 24 x 48 |  | 21.17 |  | http://m.homedepot.com/b/Lumber-Composites-Plywood-Sheathing-Plywood/21-32-in/23-32-in/N-5yc1vZc7q5Z1z0ul5eZ1z0ul6g?NCNI-5&catStyle=ShowProducts
Plywood sheathing | 23/32 | 48 x 96 |  | 22.68 |  | http://m.homedepot.com/b/Lumber-Composites-Plywood-Sheathing-Plywood/21-32-in/23-32-in/N-5yc1vZc7q5Z1z0ul5eZ1z0ul6g?NCNI-5&catStyle=ShowProducts
Linear Drain Guide | [5 empty] | http://infinitydrain.com/installation-linear-drain-guide
Linear Drain Products | [5 empty] | https://www.google.com/search?q=diy+shower+linear+drain&ie=UTF-8&oe=UTF-8&hl=en-us&client=safari
Laticrete Hydro Ban Mini Unit - 1 Gallon Pail | 1 gal |  | 1 | 81.95 | 81.95 | amazon
|  |  |  | TOTAL | 684.89 | décor island
QS60SS: Quick Slope panel 30" x 60", QS60SS, Proline Drain, White FINISH | 1/8 at drain (30" side), 1-3/8 away from drain | 30 x 60 | 3 | 79.13 | 237.39 | http://www.faucetstop.com/details.asp?productid=83714&optionid=416763&feedid=2&utm_source=google&utm_medium=cpc&utm_campaign=Shopping&gclid=CjwKEAjwgbG5BRDp3oW3qdPiuCwSJAAQmoSDX1myJKxUwGYrpFqxq_cR9XcD3UdAVO3jcBsWWv_1RBoCilDw_wcB#fo_c=877&fo_k=1967dd66fe3fc0f4b8382cba7cc86a02&fo_s=gplaus | http://www.decorisland.com/products/proline-drain/qs60ss/quick-slope-panel-30-x-60/white/?dynosearch=qs60ss
FP30P: 30" X 30" X 5/8" FLAT PANEL | 5/8" | 30x30 | 3 | 28.5 | 85.5
PLD40: 40" Trough Length, 42" Total Length, Fits R.O. 42"-46", F.O. 40"-44" | 3" wide | 42" Rough Out | 0 | 501 | 0
PVC4048D20: PROLINE DRAIN PVC4048D20 40-48" PVC DRAIN BODY WITH 2" VERTICAL OUTLET, PVC FINISH | ~3" wide | 42" Rough Out | 1 | 217 | 217
TILEIN40: 40" Tile In Strainer | 1.5" wide | 40" long | 1 | 145 | 145
SP5/8 | 5/8" height (backerboard, thinset, tile) | included with drain | na | na | na
|  |  |  | TOTAL | 133.32 | home depot
thinset mortar | 50 lb |  | 2 | 14.47 | 28.94 | home depot
Henry solar flex roof coating | 4.75 gal |  | 1 | 72 | 72 | home depot
hardie backer board | 1/4" | 3x5 | 1 | 11.87 | 11.87 | home depot
backer-on screws | #10, 1-1/4" | 200/box | 1 | 8.27 | 8.27 | home depot
backer-on screws | #10, 2" | 200/box | 1 | 8.27 | 8.27 | home depot
backer board seam tape | 2"x50' |  | 1 | 3.97 | 3.97 | home depot