## GC
GC notes
2015-12-30 | Inspector came and passed our foundation/slab at back exit. He said replacing boiler and HW with small combo unit was a good idea. Eliminate conflicts with existing panel. Cement not coming until Monday. We discussed demo chimney instead of repair and extend: even swap. Proposal for church work coming tomorrow morning.
2015-12-29 | Concrete on track for inspection Wed afternoon. Plumbing and electrical related to concrete in back should be also be ready. Discussed grading back yard. Remove timbers of raised garden. Add 6x6 timbers with dead men as a retaining wall in front of fence. Add rain leader from house to drain into retaining wall outside fence, which has a drain.
2015-12-27 | Concrete entry way, closet, and steps should be ready for concrete on Wednesday 12/30. Plumber will hopefully visit Tuesday. I asked if Oscar needed an inspection.
2015-12-27 | Follow up email on items from 12/26.
2015-12-26 | Met with Oscar and wall is being reduced. We talked about dirt being used to regrade sloping corner of yard. Oscar said he would do it.
2015-12-26 | I asked that I have a chance to request privacy windows for the master bath.
2015-12-26 | Oscar offered to put me in touch with his electrician. We also visited SPRC about the columns.
2015-12-26 | I asked that AC lines be cut and that the copper be saved for scrap sale. Oscar said ok.
2015-12-24 | North wall of back entry wall too tall. We will talk about it on Satuday 12/26
2015-12-22 | Inspector returned and passed us for concrete footings.

## Subs
| Last Name | First Name | company name | Trades | email | phone | contact date | contact | Address | reference | Licenses
1 | Ozkal | Tebessum | Lourenco Consultants | 3rd party inspections | to@lourenconsult.com | w: 202-966-0042 |  | 12/17: Filed my client information, "Notification of Intent To Use Third Party Inspection" and my building permit. | Lourenco Consultants 5171 MacArthur Blvd., NW Suite 100 Washington, DC 20016 | Raj Setty
1 | Chenault | John | Lourenco Consultants | 3rd party inspections | jc@lourenconsult.com | m: 202-412-3826 |  |  |  | Raj Setty
1 | Zahmati | Reza | MRZ Interior Design / Construction LLC | custom carpentry | design.rezazahmati@gmail.com | m: 202-370-7247 | 2016-02-29 | 2/29: Walked Reza through project. He wants to take some pictures and will submit a bid. |  | Doug Hamann
1 | Lemus | Rock | Lemus Painting Construction | Insullation, drywall, painting, flooring |  | m: 240-464-0165 | 2016-02-18 | 2/18: Walked Rock through project. He was a bit overwhelmed. He can handle insulation, drywall, painting, flooring. Maybe tile.
1 | Gable | Bob | Allied Service Co | HVAC |  | w: 202-291-1000 | 2016-01-11 | Bob visited. He diagnoses the problem as the thermostat. We need one with zero residual voltage. We have one with some low residual voltage. | 600 Gallatin St NW Washington DC 20011 | Raj Setty
1 | Mullan | Shawn | Allied Service Co | HVAC | shawnmullan@yahoo.com | m: 410-963-5365
1 | Lopez | Rudy | JBR Electric, LLC | Electrical | jbrrudylopez@yahoo.com | m: 301-537-3714 | 2015-12-29 | We reviewed proposal and my addendum, signed it, and I paid 50%. Rudy will rough out the electrical for the cement today, get the permit, and get started on the rough out for the new service location. |  | Oscar Flores
1 | Otvos | Peter | WarmBoard | In-floor radiant heating | potvos@warmboard.com | w: 831-219-1036 | 2016-01-04 | 1/4/16: Asked for and received signed relase form for CAD drawings. Shared CAD drawings and preliminary responses to questions about installation. Paid $500 design fee. 12/31/15: Began proposal process. Shared drawings pdf and gross estimates ($7.59 -Structural, $6.99 -Retrofit). Next steps: cad files ($200 fee if pdf), design ($500), and design questions. |  | Ahmann
2 | Campbell | Merrick | Bell Electric | Electrical | merrickbes@gmail.com bellelectricalservice@gmail.com | m: 301-793-3127 |  | 10/6: Contacted. VM. Sent a text. 10/16: After other attempts to make contact I learned that I had an old phone number. Raj called and handed Merrick the phone.10/19: Established contact by phone. Sent plans and arranged site visit for Wednesday 10/21 10am. 10/21: Site visit went ok. I believe we agreed he would send an estimate. 11/6: Haven't heard from Merrick since the site visit. Asked for an estimate. 11/11: Sent another ping asking for the estimate. Merrick responded same day saying he would send estimate to me by the end of the week. 11/28: Asked for estimate again 11/30: Received estimate. $26,800 12/17: Asked for ideas to reduce price. 12/21: Merrick lowered price to $24,600 or $21,500 (I buy lights and bath fans). 1/5: I told Merrick we went with another electrician. He responded, "kool no problem" |  | Raj Setty
2 | Wilcox | Steve | Wilcox Electric | Electrical | crystal@wilcox-electric.com | w: 202-546-1010 w: 301-583-8888 m: 202-664-4023 |  | 12/5: Contacted via Wilcox business website. Briefly described project and asked for a bid. 12/7: Called and set up a site visit for Dec 28 between 11:30 and 12:30. 12/28: Steve Wilcox arrived. We reviewed the project. He thought the panel needed to be moved or the hot water heater needed to be moved. He will put together a proposal in about a week. He asked me to email plans, which I did. 1/5: I received an email from Wilcox admin support saying they printed my plans. I responded that I have already signed a contract with another electrician. Admin responded with regrets. | 5602 Tuxedo Rd HYATTSVILLE MD 20781 | Angie's list (A; 294 reviews)
2 | Serrano | Eric |  | Electrical | jhadiel90@gmail.com | m: 301-693-8987 |  | 12/17: Doug put us in contact. We agreed to meet Friday 12/18 at 2pm. I sent email with plans. 12/18: We will meet 12/28 at 9:30 12/28: Eric forgot. I called him and he came quickly. We reviewed the job. He did not believe that the panel needed to be moved. He will put together a proposal in about a week. NOT AN ELECTRICIAN. Associated with licensed electrician Larry from Advanced Construction. 240-752-2588 1/5: I emailed Eric to say I signed a contract with another electrician. |  | Doug Hamann
3 | Glick | Dave | Aspen Hill Plumbing | Plumbing | info@aspenhillplumbing.com | w: 301-933-0801 m: 240-644-4673 |  | 12/5: Called late, no answer. Sent email describing project and including plans. Invited for a visit and to submit a bid. 12/7: Dave Glick (owner) responded. Offered to come Monday 2-4pm or Tuesday 7-8am. I accepted Monday 2pm. 12/8: Dave confirmed. He will call with 30 min ETA. 12/14: Site visit went well. Suggested keep the stack outside to the existing (to be moved) drain. Same with drain for utility sink. Also suggested to keep heating system simple. Will send estimate by the end of the week. Does not believe can do the work before the new year. 12/18: Dave gave estimates. Ground work and general remodel plumbing $25,750, hot water recirculating system $1850, in floor radiant heating $13,720, runtall radiators $23,040 1/5: I emailed Dave to say I signed a contract with another plumber. | 2238 Distribution Cir Silver Spring MD 20910 | Petworth Listserve + Angie's list (A; 110 reviews)
3 | Snyder | David | R&B Incorporated | A/C & Heating Sheet Metal UNICO Parts Duct Cleaning | sales@rbincorporated.com dave@rbincorporated.com | w: 703-683-1996 m: 571-238-9099 |  | 12/5: Called late, no answer. Sent email describing project and including plans. Invited for a visit. 12/7: Called. Receptionist took my name and contact. Rob called me back. We made an appointment for Thursday Dec 10 at 8am 12/10: Site visit went well. Talked a good game. Will send an estimate. | 1710 Mt Vernon Ave Alexandria VA 22301 | Petworth Listserve Angie's list (A; 62 reviews)
3 | Madrid | Otto | JPN Masonry LLC | Masonry | omadrid@jpnmasonry.com | w: 202-640-2650 m: 202-603-6072 |  |  | 2607 24th St NW Suite #2 Washington DC 20008 | Raj Setty
10 | Ramos | Martin | Ramos Plumbing & Handyman Service | Plumbing and Handyman Services | MartinRamos57@gmail.com | m: 301-768-3922 w: 301-605-7606 |  | 10/6: Established contact by phone and email. Arranged site visit for Friday 10/16 afternoon. 10/16: Site visit went well. I loaned Martin the drawings. He will return on Monday. He warned that we will have to pay for a bigger line from the street to the house for 4.5 baths. He is working on a bid. 10/21: Drawings returned. 11/6: I haven't heard from Martin. I emailed him asking for an estimate, including a seasonal maintenance visit and the cost and impact (stone retaining wall and walk) related to a new 3-inch service line. 11/28: Asked for esimate again |  | Doug Hamann
| Reyes | John | Jony Reyes Heating and Cooling | Heating and Cooling | edyleonel2013@gmail.com jonyheatandcooling@gmail.com | m: 202-355-4577 ?: 703-501-8278 h: 240-888-2741 |  | 9/16/2015: I left a message asking if interested in bidding on project 9/21/2015: We talked about the project and we planned a site visit for 9/25 9/25/2015: Jony never showed up and never contacted to explain or appologize. | 2704 Addison Dr, Oxon Hill MD 20745 | Doug Hamann | License Universal: 0502609JL
| Kelly | Tom | Jimmy Gusky LLC | Plumbing, Heating and Cooling | tjkelly858@comcast.net | m: 202-907-3292 w: 202-246-9380 |  | 9/21/2015: After I called Jimmy Gusky to see what's up, Tom Kelly emailed to say he would call the next day. He explained that he had been out of town. We arranged for a site visit on 9/25. 9/25/2015: He came and he said he would get back to me 9/28 9/30: Tom sent an email saying they would not be able to submit a bid. I asked if it was because of the Energy Verification Sheet. I said I would welcome a bid without that in the scope of work. | 1250 Taylor St NW, Washington DC | Raj Setty
| Gusky | Jimmy | Jimmy Gusky LLC | Plumbing, Heating and Cooling | jimmygusky@aol.com | m: 202-246-9380 |  | 9/16/2015: I called, described the project, and asked if interested in bidding on project. He said yes. I emailed details of bid request. | 411 Green Pasture Dr., Rockville MD | Raj Setty
| Duck | Javier |  | HVAC | javier@duckhvac.com | m: 240-672-4611 |  | 9/29/15: Contacted. Interested. Am forwarding plans. Scheduled a site visit for 10/2, 8:30-9:30 10/2: He called at 9:15 saying he would be late. Then he called asking if he could visit after he submits his bid. I asked about the EVS, and he said he was working on it. |  | Frank Cooper-Berthe
|  |  | Stevens Co. | Plumbing and Heating | richard.stevensplumbing@gmail.com | w: 202-882-4500 |  | 12/5: Called late, no answer. Sent email describing project and including plans. Invited for a visit and to submit a bid. 12/7: Called. Declined. Too busy. | 1351 Quincy St NW Washington DC 20011 | Petworth Listserve + Angie's list (A; 100 reviews)
| Swann | Russell | RSS Plumbing Solutions | HVAC & plumbing | rssplumbingsolutions@gmail.com | m: 240-882-5330 |  | 12/5: Called late, spoke briefly on the phone. Heard children. Sent text. Sent email describing project and including plans. Invited for a visit and to submit a bid. |  | Petworth Listserve
|  |  | Argent Heating & Cooling | HVAC |  | w: 703-281-6300 |  | 12/5: Called late. I briefly described the project to a receptionist. They took my number and said they would call back next week. | 501 Church Street NESuite 306 Vienna VA 22180 | Petworth Listserve Angie's list (A; 212 reviews)
| Chambers | Marlon | Climate Control Systems |  |  | w: 301-937-8292
| Silverman | Adam | Silco Electric | Electrical | adam@silcoelectric.com | w: 301-466-1128 |  | 12/5: Contacted by email. Briefly described project and asked for a bid. 12/5: Declined. Too busy. |  | Petworth Listserve + Angie's list
| McKevitt | Justin |  | HVAC/Plumbing |  | m: 240-527-0569 |  |  |  | FDA: Bobby Thompson

## Electrical
Electrical
Rudy Lopez
2016-01-05 | We reviewed proposal and my addendum, signed it, and I paid 50%. Rudy will rough out the electrical for the cement today, get the permit, and get started on the rough out for the new service location.
2016-01-04 | Rudy provided proposal. $14,900
2015-12-30 | Can't start today. On another job. He will be ready for cement on Monday. He will install phone/coax/ethernet offsetting cost bonus of the sub-panel approach.
2015-12-29 | Discussed adding a sub-panel on the third floor instead of new panel in basement. Hoped for a discoung.
2015-12-29 | Oscar Flores sent Rudy to visit. He can do the job for $14,900, not sure about fixtures, coax/ethernet. I said lets do it. He will do rough-out for sconces at steps in back right away.

## Plumbing
Plumbing
Bob Gable
2016-01-11 | Bob visited. He diagnoses the problem as the thermostat. We need one with zero residual voltage. We have one with some low residual voltage.
2016-01-10 | System still not operating properly… too cold. Bob will visit on Monday to "fine tune".
2016-01-09 | System still not operating properly… too hot. Bob stopped by and installed outdoor reset control (via exterior thermostat).
2016-01-08 | Receipt received. System not operating properly. Bob revisited bled the air out of system.
2016-01-07 | Installed Triangle tube challenger $7000 ($2700 appliance).
2016-01-04 | Bob gave his recommendation after reading the manuals for the Bosch and Triangle Tube. He recommended Triangle Tube. I said ok. He will get started. Parts delivered in about a week. Install in one day.
2016-01-03 | I said let's do Bosch. Asked when and how long it will take. I asked to talk about details. Bob called later and we talked about details. I will cc him when I email warmboard supplier.
2016-01-03 | Bob replied. $7000 to install combo boiler/dhw and $12000 for bathrooms.
2016-01-01 | Found Bosch unit. Better gpm for hot water. Name brand for parts and service. ZWB28-3. Asked for estimates related to boiler (remove existing, install new, servew new batrooms, in-floor radiant heating) and bathrooms. Asked to talk about details. Bosch Greenstar ZWB28-3A23, module IPM2 for two heating zones and mixing capability, optional concentric vent kit for horizontal direct vent
2015-12-30 | Researched 96,000 BTU Output Challenger Combo Boiler - Space Heating & Domestic Hot Water (condensing) SKU:CC-125, Brand: Triangle Tube. It costs $2659.95. Replace existing is top option.
2015-12-30 | Bob cut and capped original drain from gutters.
2015-12-29 | Bob visited. We decided to cut and cap the drain from the gutters. He will do Wed am 12/30. We talked about moving water heater options and also talked about replacing boiler with condenser boiler/hot water heater combo. He sent brochure. It is small and can go anywhere. He will get me an estimate on the main plumbing job for the new bathrooms. He will get me receipts for work.
2015-12-27 | Asked Bob to visit Tuesday when drains exposed for concrete. Asked for receipts ($500, $1500). Asked for estimates (plumbing, heating).
2015-12-23 | Change of plans. Use existing area drain. No plumbing now.
2015-12-18 | Made plan with plumber and paid him $1500 deposit.
2015-12-17 | Sent building permit number. Began relationship with inspector. Need to talk to inspector. Received estimate of project $3000.
2015-12-16 | Site visit went well. He will be able to do the project. Asked for me to send building permit #. Asked me to talk to 3rd party inspector about area drain (to sewer or to sump). He will send an estimate.
2015-12-15 | Had not heard anything. Called to see if interested. Agreed on site visit on Wed 12/16 around 4pm. Need to deal with drain in foundation.
2015-12-11 | Shawn arrived 10 minutes early and completed disconnect in 1 hour. Started to discuss rest of project and he said I should talk to his father-in-law Bob, furnace expert. Sent drawings and rfp.
2015-12-10 | Shawn Mullan called asked if he could come early, 9am.
2015-12-09 | Called. Priced the disconnect of 2 AC units at $500. Arranged the job for Friday at 10am. We will discuss rest of project.

## GCcandidates
Score | Last Name | First Name | email | phone | contact | reference | company name | notes | houzz | houzz | houzz | Angie | Angie | Angie
4.5 | Landis | Chris | heather@landisconstruction.com | 202-726-3777 | 6/26/2015: called and sent info by email 7/16/2015: sent email asking for progress update on bid 7/20/2015: ballpark estimate $400K+ minimum 1% deposit for scoping out bid in full, including details regarding finishing touches. On hold. | Toledo from church | Landis Architects/Builders |  | 4.5 stars | 15 reviews | well managed, repeat customers, complicated projects
4.5 | Leas | Mark | mleas@bethesdabuilders.com | 301-320-3770 | 6/26/2015: called and sent info by email 6/29/2015: declined, too busy | Houzz | Bethesda Builders |  | 5 stars | 8 reviews | current, mixed size, complicated projects | none | none | none
4 | Pinto | Wilgeshino | wwkconstruction@hotmail.com | 240-464-4749 | 6/26/2015: left message and sent email 6/29/2015: Will requested bidding instructions and construction plans 7/8/2015: Will backed out. Too busy | Recommended by Ahmann | WWK Construction, Inc |  | none | none | none | A for all | 4 reviews | Repeat customers, large and small projects
3.5 | Salteris | Dimitrios | dlsconstractors.inc@live.com | 301-370-7698 | 6/26/2015: no answer, sent email, dead email. | Faircloth | DLS Contractors |  | 5 stars | 7 reviews | enthusiastic but not insightful | none | none | none
3.5 | Apergis | Michael | michael@mcaremodeling.com | 301-257-2670 | 6/26/2015: left message, sent email | Faircloth | MCA Remodeling |  | none | none | none | none | none | none
3 | Khazai | Ali |  | 703-351-0909 |  | Houzz | Capital City Builders |  | 5 stars | 3 reviews | current, mixed size | none | none | none
3 | Noel | James |  | 202-834-3499 | 6/29/2015: booked until september, did not answer the phone like a business | Recommended by Ben Beiterman at Solar Solutions | Noel Design Build | Russ Clark 202-905-9103 | 5 stars | 4 reviews | current, mentioned subcontractors, and repeat business | A for all | 3 reviews | meh
3 | Flores | Oscar | oscar@omfcontractors.com | 301-937-5227 ?: 301-440-1796 | 6/29/2015: talked to secretary and sent info by email 7/2/2015: Oscar Flores emailed saying they would submit a bid in 3 weeks 7/16/2015: sent email asking for progress update on bid 7/21/2015: called asking for progress update on bid 7/21/2015: Oscar update, working with subcontractors on pricing. I will have it by the end of the week. 7/27/2015: Bid received $275K. I told him that I was having delays and would get back to him when financing and permits were ready. 9/1/2015: We met and went over some details of the project. I asked for a water-tight bid. Oscar asked to meet again. 9/8/15: Reminder about water-tight bid. Request meeting. 10/6/15: Provided the draft agreement and scope of work. Flores acknowledged receipt. 10/16/15: After several attempts to call, finally talked to Oscar. He is not available to start until Mid-December. He has not provided feedback because he is waiting for us to have the permit in hand. He is generally happy with agreement. 11/21/15: Contacted Oscar. Permit in hand. Asked for comments on agreement, schedule of values and construction schedule, and pour the foundation before ground freezes. 11/24/15: Provided response regarding agreement. | Recommended by Ahmann | OMF Contractors, Inc |  | none | none | none | none | none | none
| Mondy | Klaudia | k.mondy@omfcontractors.com | w: 301-937-5227
2 |  | Juarin |  | 240-551-6379 |  | Cheapo guy from Raj, crew of 35
2 |  | Ruben |  | 703-928-0292 |  | Divi's contractor
| Porat | Jack | ajpbuildllc@gmail.com | 301-793-2209 | 7/16/2015: called and sent info by email 8/24/2015: received bid. $329K. I asked for water-tight bid. 8/27/2015: phone call from Jack, water-tight bid is $192K 9/1/2015: Jack called and I told him I was going with a different contractor. | Parent of Adventure Camp Kid | AJP Builders (Business Card) Abraham Porat (MHIC #86242) W.H.M. Contracting Co., Inc. (DCRA # 410514000508)