## GC
Score | Last Name | First Name | email | phone | contact | reference | company name | notes | houzz | houzz | houzz | Angie | Angie | Angie
4.5 | Landis | Chris | heather@landisconstruction.com | 202-726-3777 | 6/26/2015: called and sent info by email 7/16/2015: sent email asking for progress update on bid 7/20/2015: ballpark estimate $400K+ minimum 1% deposit for scoping out bid in full, including details regarding finishing touches. On hold. | Toledo from church | Landis Architects/Builders |  | 4.5 stars | 15 reviews | well managed, repeat customers, complicated projects
4.5 | Leas | Mark | mleas@bethesdabuilders.com | 301-320-3770 | 6/26/2015: called and sent info by email 6/29/2015: declined, too busy | Houzz | Bethesda Builders |  | 5 stars | 8 reviews | current, mixed size, complicated projects | none | none | none
4 | Pinto | Wilgeshino | wwkconstruction@hotmail.com | 240-464-4749 | 6/26/2015: left message and sent email 6/29/2015: Will requested bidding instructions and construction plans 7/8/2015: Will backed out. Too busy | Recommended by Ahmann | WWK Construction, Inc |  | none | none | none | A for all | 4 reviews | Repeat customers, large and small projects
3.5 | Salteris | Dimitrios | dlsconstractors.inc@live.com | 301-370-7698 | 6/26/2015: no answer, sent email, dead email. | Faircloth | DLS Contractors |  | 5 stars | 7 reviews | enthusiastic but not insightful | none | none | none
3.5 | Apergis | Michael | michael@mcaremodeling.com | 301-257-2670 | 6/26/2015: left message, sent email | Faircloth | MCA Remodeling |  | none | none | none | none | none | none
3 | Khazai | Ali |  | 703-351-0909 |  | Houzz | Capital City Builders |  | 5 stars | 3 reviews | current, mixed size | none | none | none
3 | Noel | James |  | 202-834-3499 | 6/29/2015: booked until september, did not answer the phone like a business | Recommended by Ben Beiterman at Solar Solutions | Noel Design Build | Russ Clark 202-905-9103 | 5 stars | 4 reviews | current, mentioned subcontractors, and repeat business | A for all | 3 reviews | meh
3 | Flores | Oscar | oscar@omfcontractors.com | 301-937-5227 | 6/29/2015: talked to secretary and sent info by email 7/2/2015: Oscar Flores emailed saying they would submit a bid in 3 weeks 7/16/2015: sent email asking for progress update on bid 7/21/2015: called asking for progress update on bid 7/21/2015: Oscar update, working with subcontractors on pricing. I will have it by the end of the week. 7/27/2015: Bid received $275K. I told him that I was having delays and would get back to him when financing and permits were ready. 9/1/2015: We met and went over some details of the project. I asked for a water-tight bid. Oscar asked to meet again. 9/8/15: Reminder about water-tight bid. Request meeting. | Recommended by Ahmann | OMF Contractors, Inc |  | none | none | none | none | none | none
2 |  | Juarin |  | 240-551-6379 |  | Cheapo guy from Raj, crew of 35
2 |  | Ruben |  | 703-928-0292 |  | Divi's contractor
| Porat | Jack | ajpbuildllc@gmail.com | 301-793-2209 | 7/16/2015: called and sent info by email 8/24/2015: received bid. $329K. I asked for water-tight bid. 8/27/2015: phone call from Jack, water-tight bid is $192K 9/1/2015: Jack called and I told him I was going with a different contractor. | Parent of Adventure Camp Kid | AJP Builders (Business Card) Abraham Porat (MHIC #86242) W.H.M. Contracting Co., Inc. (DCRA # 410514000508)

## Subs
Last Name | First Name | company name | Trades | email | phone | contact | Address | reference | Licenses
Reyes | John | Jony Reyes Heating and Cooling | Heating and Cooling | edyleonel2013@gmail.com jonyheatandcooling@gmail.com | m: 202-355-4577 ?: 703-501-8278 h: 240-888-2741 | 9/16/2015: I left a message asking if interested in bidding on project 9/21/2015: We talked about the project and we planned a site visit for 9/25 9/25/2015: Jony never showed up and never contacted to explain or appologize. | 2704 Addison Dr, Oxon Hill MD 20745 | Doug Hamann | License Universal: 0502609JL
Kelly | Tom | Jimmy Gusky LLC | Plumbing, Heating and Cooling | tjkelly858@comcast.net | m: 202-907-3292 w: 202-246-9380 | 9/21/2015: After I called Jimmy Gusky to see what's up, Tom Kelly emailed to say he would call the next day. He explained that he had been out of town. We arranged for a site visit on 9/25. 9/25/2015: He came and he said he would get back to me 9/28 9/30: Tom sent an email saying they would not be able to submit a bid. I asked if it was because of the Energy Verification Sheet. I said I would welcome a bid without that in the scope of work. | 1250 Taylor St NW, Washington DC | Raj Setty
Gusky | Jimmy | Jimmy Gusky LLC | Plumbing, Heating and Cooling | jimmygusky@aol.com | m: 202-246-9380 | 9/16/2015: I called, described the project, and asked if interested in bidding on project. He said yes. I emailed details of bid request. | 411 Green Pasture Dr., Rockville MD | Raj Setty
Duck | Javier |  | HVAC | javier@duckhvac.com | m: 240-672-4611 | 9/29/15: Contacted. Interested. Am forwarding plans. Scheduled a site visit for 10/2, 8:30-9:30 10/2: He called at 9:15 saying he would be late. Then he called asking if he could visit after he submits his bid. I asked about the EVS, and he said he was working on it. |  | Frank Cooper-Berthe
Ramos | Martin | Ramos Plumbing & Handyman Service | Plumbing and Handyman Services | MartinRamos57@gmail.com | m: 301-768-3922 w: 301-605-7606 | 10/6: Established contact by phone and email. Arranged site visit for Friday 10/16 afternoon. 10/16: Site visit went well. I loaned Martin the drawings. He will return on Monday. He warned that we will have to pay for a bigger line from the street to the house for 4.5 baths. He is working on a bid. |  | Doug Hamann
Campbell | Merrick | Bell Electric | Electrical | merrickbes@gmail.com | m: 301-793-3127 | 10/6: Contacted. VM. Sent a text. 10/16: After other attempts to make contact I learned that I had an old phone number. Raj called and handed Merrick the phone.10/19: Established contact by phone. Sent plans and arranged site visit for Wednesday 10/21 10am. |  | Raj Setty
Madrid | Otto | JPN Masonry LLC | Masonry | omadrid@jpnmasonry.com | w: 202-640-2650 m: 202-603-6072 |  | 2607 24th St NW Suite #2 Washington DC 20008 | Raj Setty