## budget
| Total budget |  |  |  |  | 135488.96 |  | 147370.1 | 111900
Division | Description | qty | unit cost | Paid Date | Paid Check | Actual | Actual Subtotals | My Budget | Raj's Budget | Notes
Pre 1: | Architect and Permits
Budget
29350 | Ahmann: SE Application Fee, remaining balance |  |  | 2015-12-10 | bill pay | 829.45 |  |  |  | Email invoice 12/05/14
Actual | Ahmann: Zoning Relief Phase (Phase 3), retainer applied |  |  | 2014-11-18 | bill pay | 1109.08 |  |  |  | Email invoice 11/12/14
32019.52 | Ahmann: Zoning Analysis and Design (Phase 2) |  |  | 2014-08-15 | bill pay | 3668 |  |  |  | Can't find
| Ahmann: Measured Drawings (Phase 1) |  |  | 2014-07-03 | bill pay | 2810.5 |  |  |  | Email invoice 6/27/15
| Ahmann: Retainer |  |  | 2014-06-17 | 2099 | 2000 |  |  |  | Original Contract: email 5/14/14
| Ahmann | [5 empty] | 10417.03 | 9850 | 0
| Ahmann: Permints complete |  |  | 2015-11-23 | HELOC, 8002 | 2130.13
| Ahmann: Permits near completion |  |  | 2015-09-08 | bill pay | 2400.36 |  |  |  | Email invoice 6/24/15
| Ahmann: Construction Plans |  |  | 2015-06-29 | 2139 | 6875
| Ahmann: Structural Engineering |  |  | 2015-06-29 | 2139 | 2000
| Ahmann: Construction Plans |  |  | 2015-05-11 | bill pay | 6197 |  |  |  | Paper Invoice and email
| Ahmann: Retainer |  |  | 2015-03-30 | bill pay | 2000 |  |  |  | Original Contract: email 1/20/15
| Ahmann | [5 empty] | 21602.49 | 16500 | 5000
| Currie & Associates |  |  | 2014-10-03 | bill pay | 300
| Currie & Associates |  |  | 2014-09-22 | 2106 | 850
| Geotech Engineers Soil Testing |  |  | 2015-06-26 | 2137 | 700 |  |  |  | original invoice in email 3/26/15
| Geotech Engineers Soil Testing |  |  | 2015-04-03 | 2129 | 700 |  |  |  | invoice in email 6/11/15
| inspections | 10 | 300 |  |  |  |  | 3000 | 0 | http://dcra.dc.gov/node/514182
Pre 2: | Solar
6877.5
| Solar Solution |  |  | 2015-04-27 | 2133 | 2598.75 |  |  |  | Paper invoice
| Solar Solution | [5 empty] | 2598.75 | 17325
| Upfront SREC Credit | [6 empty] | -5250
| Solar Tax Credit | [6 empty] | -5197.5
Pre 3: | Miscellaneous
14400
| misc. tools | [6 empty] | 8000 | 8000
| trash - 10 pulls | 4 | 350 |  |  |  |  | 1400 | 0
2 | earth and cement | [6 empty] | 5000 | 0 | 250
5000 | move fence | [7 empty] | 0
| misc. clearing and grubbing | [7 empty] | 0
| demo walk in front | [7 empty] | 0
| dig new posts for front deck | [7 empty] | 0
| side concrete - foundation | [7 empty] | 3000 | 6500
| rear concrete foundation | [7 empty] | 3500 | http://www.vcs-va.com/
| CMU lf - rear | [7 empty] | 4100 | sisler/materials
| CMU lf - side | [7 empty] | 0
3 | landscaping | [6 empty] | 5000
5000
4 | framing walls |  |  |  |  | 13003.58 |  | 7000 | 14000
10000 | AC closet
| framing roof | [6 empty] | 0 | 0
| interconnect | [6 empty] | 0 | 0
| trim |  |  |  |  | 14.8 |  | 2500 | 4500
| shoe molding | [6 empty] | 500 | 500
5 | labor | [6 empty] | 60000
#REF! | Doug | 400 | 35 | [5 empty] | 0
avg. rate | Roy | 400 | 27 | [5 empty] | 0
22.5714 | roy helper | 40 | 19 | [5 empty] | 0
| Doug labor - Ramon beltran | 180 | 17 | [5 empty] | 0
| edwin | 500 | 25 | [5 empty] | 0
| edwin labor | 600 | 20 | [5 empty] | 0
| edwin labor 2 | 440 | 15 | [5 empty] | 0
| #REF! | weeks left of labor money
6 | closets | [6 empty] | 500 | 2000 | container store
2000 | window treatments |  |  |  |  | 68.26 |  | 1500 | 1500
7 | windows
#REF! | existing | 22 | 400 |  |  | 20258.46 |  |  | 10800 | http://www.windowestore.com/
| upper new | 11 | 500 | [5 empty] | 0 | home depot - anderson
| lower new | 9 | 450 | [5 empty] | 0
8 | doors | 240 | 5280
#REF! | interior doors
| master bath new - 25" | 1 | 165 | [5 empty] | 0
| 30" | 8 | 165 |  |  | 1192.37 |  |  | 0
| hardware | 20 | 85 | [5 empty] | 1200
| Closet Doors | 6 | 150 | [5 empty] | 0
exterior doors
| 81x61 - french door | 0 | 1000 | [5 empty] | 0
| front door(84x26), clg hgt 96" | 1 |  |  |  | 464.47 |  |  | 2000
| 84x62.75 - french door - kit ex. | 1 | 1000 | [5 empty] | 0
| ext. door hardware | 5 | 150 | [5 empty] | 0
9
#REF! | paint
| upper | 3240 |  |  |  | 1000 |  |  | 1000
| lower | 1650 |  |  |  | 39.2 |  |  | 1500
| materials |  |  |  |  | 163.38 |  |  | 500
| Hardwood flooring | 1500 | 9 | [5 empty] | 0 | mygirlsflooring.com
| carpet | [7 empty] | 2500 | 301-861-0220
| drywall (250 sheets-TBV) | 4890 | 1 | [5 empty] | 0
Fix Chimney
cornice
| roofing/gutters | 1500 | 14 |  |  | 22500 |  |  | 0 | pale's roofing
| metal roofing | 500 | 5.5 | [5 empty] | 1500 | 240-882-2078
| solar panels | [6 empty] | 6878 |  | $17,325 upfront, $5,250 SREC credit, $5,197.5 Fed Tax credit
Fence Panel, Delivery Access, Security
| tile - bathrooms lower | 200 | 8 |  |  | 58.67 |  |  | 0 |  | x
| tile - bathrooms master | 400 | 8 | [5 empty] | 0
| entry hall | 50 | 8 | [5 empty] | 0
pebble mosiac = $5/sf, mixed glass/stone$7/sf,solid granite$4.25/sf, gray marble$4.5/sf,largewhglass$7/sf, travertine$1000/181sf, rough wood looking floor tile $3/sf
| deck ceiling | 500 | 6 | [5 empty] | 0
| Sheathing | 1500 | 3 | [5 empty] | 500
| hardie - rear and front | 720 | 3 |  |  | 4504.99 |  |  | 0
| hardie - sides | 783 | 3 | [5 empty] | 0
| hardie plank | 2250
| tyvek | [7 empty] | 0 | go to tristate
| decking - Trex - upper part | [7 empty] | 500
| handrails/cedar millwork |  |  |  |  | 4914.87 |  |  | 5000
| millwork | [7 empty] | 2000
| deck stairs | [7 empty] | 500
| insulation |  |  |  |  | 200 |  |  | 6500 | http://www.sprayfoamkit.com/land/kit_602_video.html
foam it green
Plumbing & Mechanical
15
#REF! | disconnect 2 AC units |  |  |  |  | 500 |  |  | 2000 | 12/11: Allied Service Company
| ductwork |  |  |  |  | 923.35 |  | 923.35 | 2000
HVAC
| radiant floor upstairs | 500 | 7 |  |  | 539 |  | 539 | 0
| radiant floor downstairs | 350 | 5 |  |  | 466.36 |  | 466.36 | 0
| move/new radiators | 3 base (UF-6 18"x36"), 1 shower |  |  |  | 3095 |  | 3095 | 3100 | http://www.runtalnorthamerica.com/residential_radiators/baseboard_uf.html
| toilets | 3 | 400 |  |  | 1197.66 |  | 1197.66 | 0
| shower | 2 | 500 | [5 empty] | 0
#REF! | infinity drain | 1 | 500 | [5 empty] | 0
plumb | sink | 3 | 1000 |  |  | 1750.9 |  | 1750.9 | 0
| W/D with vent | 1 | 1900 |  |  | 1892.33 |  | 1892.33 | 1900
| new tub | 1 | 1000 | [5 empty] | 0
| misc. plumb |  |  |  |  | 3000 |  | 3000 | 4000 | allied - bob
16 | Lights | 25 | 250 | [5 empty] | 5000
#REF! | rough-in |  |  |  |  | 13800 |  |  | 5000
| elec. Materials |  |  |  |  | 0 |  |  | 2000
| misc. elec |  |  |  |  | 3.04 |  |  | 2000
| move main power |  |  |  |  | 2770 |  |  | 2800 | 202-331-6237
202-388-2642
| contingency/escalation | [7 empty] | 0 | ken murray
| Total budget |  |  |  |  | 135488.96 |  | 147370.1 | 111900
Note on G104: Raj: roc windows 12/12,

## cash
Accounts | Updated 7/26/2015
| balance | rate | monthly payment
refinance | 121286.96
Schwab Brokerage | 28561
equity line | 67000 | 3% | 0.25% below prime
TSP loan | 50000 | 2.125% | 812
total liquid |  |  |  | 266847.96
prosper | 35383 |  |  | Stopped reinvesting on 7/7/15. Cash balance $3000 on 8/23. Cash available is $2000 per month
Schwab Inh IRA | 138629
Schwab Roth | 111367
TSP | 260000
FERS
total total |  |  |  | 812226.96
Debt | Updated 7/26/2015
| balance | rate | monthly payment
Mortgage | 405000 | 3.85% | 2632 | I can offset this (increase) by taking distributions from my Prosper account.
HELOC | 67000 | ?3.85? | 500 | I can offset this by taking distributions from my Prosper account.
TSP loan | 50000 | 2.125% | 812 | I can offset this by reducing TSP constributions (currently $660)
E: Student Loan | 30000 | 3% | 260
E: Car Loan | 23600 | 1.5% | 593
total | 575600 |  | 4797 | 575600
Income Retirement | Updated 7/26/2015
| balance | rate | monthly payment
TSP | 260000 |  | 1329 | $4800/month projected monthly payment assuming continued savings
Social Security |  |  | 2403 | Assuming work until 67. At 62 can receive $1566/month.
FERS |  |  | 2475 | Assuming work until 65. At 62 can receive 2235/month.
Charles Schwab Retirement Planning Calculator |  |  | https://client.schwab.com/Areas/Accounts/RetirementAssessment/YourInfo.aspx
Retirement age | 65
Life Expectancy | 90
Current salary | 134662
effective tax rate from paystub | 22.28%
Tax-advantaged retirement savings | 509996 |  | Includes TSP, Roth, and Schwab Inh IRA. Does not include FERS
Total amount you/your employer contribute annually | 29160 |  | From paystub (me+gov+gov) and IRA contribution
Taxable savings intended for retirement | 63944 |  | Includes prosper and brokerage
Yearly taxable savings for retirement | 0
Moderate-aggressive pre-retirement
Moderate-conservative after retirement
% current income, retirement spending |  | 100%
Soc Sec Ben |  |  | Calculate automatically. Begin receiving at 67
Retirement income | 0
Retirement Savings Projected | Report 7/26/2015 |  |  | 1720237
Retirement Savings Needed |  |  |  | 1380871
Surplus Retirement |  |  |  | 339366
Project Size
first | 1038 | 39400% | sf
second | 825 | 49000% | sf
total existing | 1863 | 88400% | sf
TOTAL BUILDING | 2747
$500/sf | 1373500

## WaterTight
Building Envelope
2015-07-25 | scheule for windows and doors sent and estimate requested
| steve | 84 LUMBER CO. #0913: | 5321 MARLBORO PIKE, UPPER MARLBORO, MD 20772 (17.36 mi) | 301-952-0584 | marinos@0913.84lumber.com
|  | LAMAR & WALLACE, INC. | 7000 OLD LANDOVER ROAD LANDOVER,MD 20785-1504 | 301-772-2400
|  | GALLIHER & HUGUELY ASSOCIATES, INC. | 5925 BLAIR RD. NW WASHINGTON,DC 20011-2343 | 202-723-1000
[12 empty] | total | 5.75% tax
| Windows |  | Jeld-Wen quote from Galliher & Hugueley | 5434.2176 | [7 empty] | 5138.74 | 295.4776
|  |  |  | Required | Provided |  |  | Need sash limiters
|  | Plans Pg A-0 | Energy Conservation | U-Factor = 0.35 | TBD |  |  | Quote based on 4-9/16" jambs.
|  | Plans Pg A-4 | Window and Exterior Door Schedule |  |  |  |  | what are the jamb sizes?
Floor | Room | ID in plans | Description and model from architect | Description and model from owner | Description and model from supplier | Planned width | Planned width | Rough opening width | Rough opening height | # items | cost per item | total cost | delivery time
Third Floor | Bedroom | 1 | Jeld-Wen 2-3756 with 5-1/2" mull: Double Hung Window | Jeld-Wen: W-2500, Two Double Hung windows with 5.5" mull. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 78" | 54" | 76.25" | 56.75" | 1 | 740.75 | 740.75 | 3-4 weeks
First Floor | Sun Room | 2.A1 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, Two mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" | 40.75" | 54.75" | 2 | 599.66 | 1199.32 | 3-4 weeks
First Floor | Sun Room | 2.A2 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" |  |  | 0 |  | 0 | 3-4 weeks
First Floor | Sun Room | 2.A3 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, Two mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 96" |  |  | 0 |  | 0 | 3-4 weeks
First Floor | Sun Room | 2.A4 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 42" | 96" |  |  | 0 |  | 0 | 3-4 weeks
Second Floor | Master Bath | 2.B | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, 2 mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" | 40.75" | 54.75" | 3 | 599.66 | 1798.98 | 3-4 weeks
First Floor | Sun Room | 3 | Jeld-Wen 1754 fixed | Jeld-Wen: W-2500, one casement window, fixed, no grille, white | Jeld-Wen: see quote | 12" to 18" | 60" | 20.75" | 54.75" | 2 | 254.9 | 509.8 | 3-4 weeks
First Floor | Sun Room | 3 | Jeld-Wen 1754 fixed | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 12" to 18" | 60" |  |  | 2 |  | 0 | 3-4 weeks
Third Floor | Bedroom | 4.A | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks
Third Floor | Recreation room | 4.B | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks
Third Floor | Bathroom | 4.C | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks
[12 empty] | total | 5.75% tax
| Doors |  | Lemieux, Masonite quote from Galliher & Hugueley | 2526.3675 | [7 empty] | 2389 | 137.3675
|  |  |  | Required | Provided |  |  | Can I remove T-astragal?
|  | Plans Pg A-0 | Energy Conservation | U-Factor = 0.35 | TBD |  |  | Quote based on 4-9/16" jambs.
what are the jamb sizes?
|  | Plans Pg A-4 | Window and Exterior Door Schedule
Floor | Room | ID in plans | Description and model from architect | Description and model from owner | Description and model from supplier | Planned width | Planned height | Width from supplier | Height from supplier | # items | cost per item | total cost | delivery time
Basement | Exit | A | Basement panel door with glass | Smooth-pro fiberglass panel exterior door, 1/2 view 9-light, 1-panel, screened | Masonite BLS-106-09I | 3' | 6'-8" | 3' | 6'-8" | 0 | 442 | 0 | 4-6 weeks
Basement | Exit | A.alternate | Basement panel door with glass | Authentic wood glass panel exterior door 5209 | Lemieux F5944 | 3' | 6'-8" | 3' | 6'-8" | 1 | 650 | 650 | 4-6 weeks
First Floor | Sun Room | B | Hinged patio door (inswing) Transom (3'x1') mulled above | Door from existing 2nd fl bedroom exit Security storm door from existing kitchen exit Transom (2'-6" x 1'-4") mulled above | Does current door with security storm door pass U-Factor? | 2'-6" | 6'-8" | 2'-6" | 6'-8" | 1 | 0 | 0 | EXISTING
First Floor | Sun Room | B.alternate | Hinged patio door (inswing) Transom (3'x1') mulled above | Hinged patio door (inswing) Transom (3'x1') mulled above | Lemieux 5001 W/Transom | 3' | 7' | 3' | 7' | 0 | 698 | 0 | 1-2 weeks
Third Floor | Exit To Balcony | C | Hinged patio door (inswing, 2-panel) | Authentic wood glass panel exterior door 5001 | Lemieux 5001 W/T-astragal | 6' | 6'-8" | 6' | 6'-8" | 1 | 949 | 949 | 1-2 weeks
Basement | Outside Under Sun Room | D | Paneled storage doors (inswing) | Smooth-pro fiberglass panel exterior door, 2-panel square top (match other basement door, no window) | Masonite 2-panel smooth fiberglass with T-astragal and slide bolt Can I remove the T-astragal? | 5' | 6'-8" | 5' | 6'-8" | 1 | 790 | 790 | 4-6 weeks
Roofs/Ceilings
Floor | Room | ID in plans | Desc | Detailed Description | Source and delivery |  |  | Width nominal (ft) | Height nominal (ft) | total (sf) | cost per sf: materials, supplies, tools |  | cost total
Estimates from | http://www.homewyse.com/
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | R-38 OR R-38C (10 1/4" HIGH DENSITY BATT) AT ATTIC AS ALLOWED BY EXISTING CLEARANCE, 2X8 rafters |  |  |  | 20 | 36 | 720 | 1.15 |  | 828
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | R-38 OR R-38C (10 1/4" HIGH DENSITY BATT) AT ATTIC AS ALLOWED BY EXISTING CLEARANCE, 2X8 rafters |  |  |  | 9 | 76 | 684 | 1.15 |  | 786.6
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | 6 1/2" CLOSED CELL SPRAY FOAM (R38) ABOVE TOP PLATES AT EAVE, 2X8 rafters @ eaves |  |  |  | 8 | 16 | 128 | 1.15 |  | 147.2
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 20 | 36 | 720 | 3 |  | 2160 | homewyse says $3/sf for materials, tools, supplies
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 9 | 76 | 684 | 3 |  | 2052
Second floor | Flat roof | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 8 | 16 | 128 | 3 |  | 384
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Fiberglass shingles |  |  |  |  | 9 | 76 | 684 | 3 |  | 2052
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 20 | 36 | 720 | 0.5 |  | 360
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 9 | 76 | 684 | 0.5 |  | 342
Second floor | Flat roof | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 8 | 16 | 128 | 0.5 |  | 64
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Balcony floor | Duradek walkable floor membrane |  |  |  | 8 | 16 | 128 | 10.5 |  | 1344
Walls (Wood Framing)
|  |  |  | Required | Provided
|  |  | Energy Conservation | R-Value = R-20 or R-13+5 | R-21, 2X6 frame walls
Mass Walls
|  | Plans Pg A-0 | Energy Conservation, Required R-Value = R-8/13
Second floor | Master Bath | Plans Pg A-5
Basement Walls
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10/13 | N/A
Floors
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-19 | R-Value = R-30, 2X10 floor joists
Slab Perimeter R-value and Depth
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10, 2FT depth | N/A
Crawl Space
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10/13 | N/A
Infiltration
ALL EXTERIOR JOINTS SHALL HAVE A HIGH QUALITY DETAILED, AIR SEALING APPLIED TO INCLUDE BUT NOT LIMITED TO PICTURE FRAMING STUDS, BOTTOM PLATES, TOP PLATES, AROUND WINDOWS AND DOORS, EXHAUST PENETRATIONS, WIRING PENETRATIONS OSB GAPS, RIM JOISTS, AND NAIL-HOLES

## Flores
Original Bid |  | Water-tight Bid
1. DIVISION 1: General requirements | 17000 | 17000
2. DIVISION 2: Demolition and sitework | 15025 | 15025
3. DIVISION 3: Concrete | 8500 | 8500
4. DIVISION 4: Masonry | 13125 | 13125
5. DIVISION 5: Metals | 1800
6. DIVISION 6: Wood/ Carpentry | 65075 | 65075
7. DIVISION 7: Thermal and moister protection | 19840 | 19840 | This is an overestimate because it does not include insulation.
8. DIVISION 8: Doors and windows | 14300 | 14300
9. DIVISION 9: Finishes and accessories | 15080
10. DIVISION 10 -14: Not included | 0
11. DIVISION 15: Plumbing and Mechanical | 32000 | 1000 | This is an uneducated guess.
12. DIVISION 16: Electrical | 15500
13. ALLOWANCES: | 10240
 Ceramic tile – 360 Sf @ $ 7.50 p/Sf = $ 2,700.00 |  | 0
 Counter top slab – 16 Sft @ $ 65.00 = $ 1,040.00 |  | 0
 Plumbing fixtures and bath accessories - $ 5,000.00 |  | 0
 Bath vanities for powder room and master bath - $ 1,500.00 |  | 0
0
TOTAL | 227485 | 153865
14. OVERHEAD AND PROFIT- 20% | 45497 | 30773
Compare to
GRAND TOTAL | 272982 | 184638 | 174000