## GC
Score | Last Name | First Name | email | phone | contact | reference | company name | notes | houzz | houzz | houzz | Angie | Angie | Angie
4.5 | Landis | Chris | heather@landisconstruction.com | 202-726-3777 | 6/26/2015: called and sent info by email 7/16/2015: sent email asking for progress update on bid 7/20/2015: ballpark estimate $400K+ minimum 1% deposit for scoping out bid in full, including details regarding finishing touches. On hold. | Toledo from church | Landis Architects/Builders |  | 4.5 stars | 15 reviews | well managed, repeat customers, complicated projects
4.5 | Leas | Mark | mleas@bethesdabuilders.com | 301-320-3770 | 6/26/2015: called and sent info by email 6/29/2015: declined, too busy | Houzz | Bethesda Builders |  | 5 stars | 8 reviews | current, mixed size, complicated projects | none | none | none
4 | Pinto | Wilgeshino | wwkconstruction@hotmail.com | 240-464-4749 | 6/26/2015: left message and sent email 6/29/2015: Will requested bidding instructions and construction plans 7/8/2015: Will backed out. Too busy | Recommended by Ahmann | WWK Construction, Inc |  | none | none | none | A for all | 4 reviews | Repeat customers, large and small projects
3.5 | Salteris | Dimitrios | dlsconstractors.inc@live.com | 301-370-7698 | 6/26/2015: no answer, sent email, dead email. | Faircloth | DLS Contractors |  | 5 stars | 7 reviews | enthusiastic but not insightful | none | none | none
3.5 | Apergis | Michael | michael@mcaremodeling.com | 301-257-2670 | 6/26/2015: left message, sent email | Faircloth | MCA Remodeling |  | none | none | none | none | none | none
3 | Khazai | Ali |  | 703-351-0909 |  | Houzz | Capital City Builders |  | 5 stars | 3 reviews | current, mixed size | none | none | none
3 | Noel | James |  | 202-834-3499 | 6/29/2015: booked until september, did not answer the phone like a business | Recommended by Ben Beiterman at Solar Solutions | Noel Design Build | Russ Clark 202-905-9103 | 5 stars | 4 reviews | current, mentioned subcontractors, and repeat business | A for all | 3 reviews | meh
3 | Flores | Oscar | oscar@omfcontractors.com | 301-937-5227 ?: 301-440-1796 | 6/29/2015: talked to secretary and sent info by email 7/2/2015: Oscar Flores emailed saying they would submit a bid in 3 weeks 7/16/2015: sent email asking for progress update on bid 7/21/2015: called asking for progress update on bid 7/21/2015: Oscar update, working with subcontractors on pricing. I will have it by the end of the week. 7/27/2015: Bid received $275K. I told him that I was having delays and would get back to him when financing and permits were ready. 9/1/2015: We met and went over some details of the project. I asked for a water-tight bid. Oscar asked to meet again. 9/8/15: Reminder about water-tight bid. Request meeting. 10/6/15: Provided the draft agreement and scope of work. Flores acknowledged receipt. 10/16/15: After several attempts to call, finally talked to Oscar. He is not available to start until Mid-December. He has not provided feedback because he is waiting for us to have the permit in hand. He is generally happy with agreement. 11/21/15: Contacted Oscar. Permit in hand. Asked for comments on agreement, schedule of values and construction schedule, and pour the foundation before ground freezes. 11/24/15: Provided response regarding agreement. | Recommended by Ahmann | OMF Contractors, Inc |  | none | none | none | none | none | none
| Mondy | Klaudia | k.mondy@omfcontractors.com | w: 301-937-5227
2 |  | Juarin |  | 240-551-6379 |  | Cheapo guy from Raj, crew of 35
2 |  | Ruben |  | 703-928-0292 |  | Divi's contractor
| Porat | Jack | ajpbuildllc@gmail.com | 301-793-2209 | 7/16/2015: called and sent info by email 8/24/2015: received bid. $329K. I asked for water-tight bid. 8/27/2015: phone call from Jack, water-tight bid is $192K 9/1/2015: Jack called and I told him I was going with a different contractor. | Parent of Adventure Camp Kid | AJP Builders (Business Card) Abraham Porat (MHIC #86242) W.H.M. Contracting Co., Inc. (DCRA # 410514000508)

## Subs
Last Name | First Name | company name | Trades | email | phone | contact | Address | reference | Licenses
Reyes | John | Jony Reyes Heating and Cooling | Heating and Cooling | edyleonel2013@gmail.com jonyheatandcooling@gmail.com | m: 202-355-4577 ?: 703-501-8278 h: 240-888-2741 | 9/16/2015: I left a message asking if interested in bidding on project 9/21/2015: We talked about the project and we planned a site visit for 9/25 9/25/2015: Jony never showed up and never contacted to explain or appologize. | 2704 Addison Dr, Oxon Hill MD 20745 | Doug Hamann | License Universal: 0502609JL
Kelly | Tom | Jimmy Gusky LLC | Plumbing, Heating and Cooling | tjkelly858@comcast.net | m: 202-907-3292 w: 202-246-9380 | 9/21/2015: After I called Jimmy Gusky to see what's up, Tom Kelly emailed to say he would call the next day. He explained that he had been out of town. We arranged for a site visit on 9/25. 9/25/2015: He came and he said he would get back to me 9/28 9/30: Tom sent an email saying they would not be able to submit a bid. I asked if it was because of the Energy Verification Sheet. I said I would welcome a bid without that in the scope of work. | 1250 Taylor St NW, Washington DC | Raj Setty
Gusky | Jimmy | Jimmy Gusky LLC | Plumbing, Heating and Cooling | jimmygusky@aol.com | m: 202-246-9380 | 9/16/2015: I called, described the project, and asked if interested in bidding on project. He said yes. I emailed details of bid request. | 411 Green Pasture Dr., Rockville MD | Raj Setty
Duck | Javier |  | HVAC | javier@duckhvac.com | m: 240-672-4611 | 9/29/15: Contacted. Interested. Am forwarding plans. Scheduled a site visit for 10/2, 8:30-9:30 10/2: He called at 9:15 saying he would be late. Then he called asking if he could visit after he submits his bid. I asked about the EVS, and he said he was working on it. |  | Frank Cooper-Berthe
Ramos | Martin | Ramos Plumbing & Handyman Service | Plumbing and Handyman Services | MartinRamos57@gmail.com | m: 301-768-3922 w: 301-605-7606 | 10/6: Established contact by phone and email. Arranged site visit for Friday 10/16 afternoon. 10/16: Site visit went well. I loaned Martin the drawings. He will return on Monday. He warned that we will have to pay for a bigger line from the street to the house for 4.5 baths. He is working on a bid. 10/21: Drawings returned. 11/6: I haven't heard from Martin. I emailed him asking for an estimate, including a seasonal maintenance visit and the cost and impact (stone retaining wall and walk) related to a new 3-inch service line. 11/28: Asked for esimate again |  | Doug Hamann
|  | Stevens Co. | Plumbing and Heating | richard.stevensplumbing@gmail.com | w: 202-882-4500 | 12/5: Called late, no answer. Sent email describing project and including plans. Invited for a visit and to submit a bid. 12/7: Called. Declined. Too busy. | 1351 Quincy St NW Washington DC 20011 | Petworth Listserve + Angie's list (A; 100 reviews)
Glick | Dave | Aspen Hill Plumbing | Plumbing | info@aspenhillplumbing.com | w: 301-933-0801 | 12/5: Called late, no answer. Sent email describing project and including plans. Invited for a visit and to submit a bid. 12/7: Dave Glick (owner) responded. Offered to come Monday 2-4pm or Tuesday 7-8am. I accepted Monday 2pm. 12/8: Dave confirmed. He will call with 30 min ETA. | 2238 Distribution Cir Silver Spring MD 20910 | Petworth Listserve + Angie's list (A; 110 reviews)
Swann | Russell | RSS Plumbing Solutions | HVAC & plumbing | rssplumbingsolutions@gmail.com | m: 240-882-5330 | 12/5: Called late, spoke briefly on the phone. Heard children. Sent text. Sent email describing project and including plans. Invited for a visit and to submit a bid. |  | Petworth Listserve
|  | Argent Heating & Cooling | HVAC |  | w: 703-281-6300 | 12/5: Called late. I briefly described the project to a receptionist. They took my number and said they would call back next week. | 501 Church Street NESuite 306 Vienna VA 22180 | Petworth Listserve Angie's list (A; 212 reviews)
Snyder | David | R&B Incorporated | A/C & Heating Sheet Metal UNICO Parts Duct Cleaning | sales@rbincorporated.com dave@rbincorporated.com | w: 703-683-1996 m: 571-238-9099 | 12/5: Called late, no answer. Sent email describing project and including plans. Invited for a visit. 12/7: Called. Receptionist took my name and contact. Rob called me back. We made an appointment for Thursday Dec 10 at 8am | 1710 Mt Vernon Ave Alexandria VA 22301 | Petworth Listserve Angie's list (A; 62 reviews)
Gable | Bob | Allied Service Co | HVAC | shawnmullan@yahoo.com | w: 202-291-1000 m: 410-963-5365 | 12/9: Called. Priced the disconnect of 2 AC units at $500. Arranged the job for Friday at 10am. We will discuss rest of project. 12/10: Shawn Mullan called asked if he could come early, 9am. 12/11: Shawn arrived 10 minutes early and completed disconnect in 1 hour. Started to discuss rest of project and he said I should talk to his father-in-law Bob, furnace expert. Sent drawings and rfp. | 600 Gallatin St NW Washington DC 20011 | Raj Setty
Chambers | Marlon | Climate Control Systems |  |  | w: 301-937-8292
Campbell | Merrick | Bell Electric | Electrical | merrickbes@gmail.com bellelectricalservice@gmail.com | m: 301-793-3127 | 10/6: Contacted. VM. Sent a text. 10/16: After other attempts to make contact I learned that I had an old phone number. Raj called and handed Merrick the phone.10/19: Established contact by phone. Sent plans and arranged site visit for Wednesday 10/21 10am. 10/21: Site visit went ok. I believe we agreed he would send an estimate. 11/6: Haven't heard from Merrick since the site visit. Asked for an estimate. 11/11: Sent another ping asking for the estimate. Merrick responded same day saying he would send estimate to me by the end of the week. 11/28: Asked for estimate again 11/30: Received estimate. $26,800 |  | Raj Setty
|  | Wilcox Electric | Electrical |  | w: 202-546-1010 | 12/5: Contacted via Wilcox business website. Briefly described project and asked for a bid. 12/7: Called and set up a site visit for Dec 28 between 11:30 and 12:30. | 5602 Tuxedo Rd HYATTSVILLE MD 20781 | Angie's list (A; 294 reviews)
Silverman | Adam | Silco Electric | Electrical | adam@silcoelectric.com | w: 301-466-1128 | 12/5: Contacted by email. Briefly described project and asked for a bid. 12/5: Declined. Too busy. |  | Petworth Listserve + Angie's list
Madrid | Otto | JPN Masonry LLC | Masonry | omadrid@jpnmasonry.com | w: 202-640-2650 m: 202-603-6072 |  | 2607 24th St NW Suite #2 Washington DC 20008 | Raj Setty