## budget
| Total budget |  |  |  |  | 211902.6 | 150371.4 |  | 319326.79 | Target < $300,000 !!!
Division | Description | qty | unit cost | Paid Date | Paid Check | Actual | Actual OMF Contractor | Actual Subtotals | My Budget | Notes
Pre 1: | Architect and Permits
Budget
33418.14
Actual
36500.16
| Ahmann: SE Application Fee, remaining balance |  |  | 2015-12-10 | bill pay | 829.45 |  |  |  | Email invoice 12/05/14
| Ahmann: Zoning Relief Phase (Phase 3), retainer applied |  |  | 2014-11-18 | bill pay | 1109.08 |  |  |  | Email invoice 11/12/14
| Ahmann: Zoning Analysis and Design (Phase 2) |  |  | 2014-08-15 | bill pay | 3668 |  |  |  | Can't find
| Ahmann: Measured Drawings (Phase 1) |  |  | 2014-07-03 | bill pay | 2810.5 |  |  |  | Email invoice 6/27/15
| Ahmann: Retainer |  |  | 2014-06-17 | 2099 | 2000 |  |  |  | Original Contract: email 5/14/14
| Ahmann | [6 empty] | 10417.03 | 9850
| Ahmann: Review Doors & Windows purchase, Party Wall Change Order |  |  | 2016-03-16 | HELOC, 107 | 412.5 |  |  |  | Email invoice 3/21/16
| Ahmann: Permints complete |  |  | 2015-11-23 | HELOC, 8002 | 2130.13
| Ahmann: Permits near completion |  |  | 2015-09-08 | bill pay | 2400.36 |  |  |  | Email invoice 6/24/15
| Ahmann: Construction Plans |  |  | 2015-06-29 | 2139 | 6875
| Ahmann: Structural Engineering |  |  | 2015-06-29 | 2139 | 2000
| Ahmann: Construction Plans |  |  | 2015-05-11 | bill pay | 6197 |  |  |  | Paper Invoice and email
| Ahmann: Retainer |  |  | 2015-03-30 | bill pay | 2000 |  |  |  | Original Contract: email 1/20/15
| Ahmann | [6 empty] | 22014.99 | 16500
| Currie & Associates | 1 | 300 | 2014-10-03 | bill pay | 300 |  |  | 300
| Currie & Associates | 1 | 850 | 2014-09-22 | 2106 | 850 |  |  | 850
| Geotech Engineers Soil Testing | 1 | 700 | 2015-06-26 | 2137 | 700 |  |  | 700 | original invoice in email 3/26/15
| Geotech Engineers Soil Testing | 1 | 700 | 2015-04-03 | 2129 | 700 |  |  | 700 | invoice in email 6/11/15
| inspections | 10 | 300 | [5 empty] | 3000 | http://dcra.dc.gov/node/514182
| GEICO insurance | 1 | 1418.14 | 2015-12-11 | HELOC cc | 1418.14 |  |  | 1418.14
| Appliances diagnoses | 1 | 100 | 2015-12-30 | HELOC 101 | 100 |  |  | 100 | Appliance Services Inc, 202-409-6056 Dishwasher not fixable, stove needs spark module and 3 switches ($255-50), fridge needs water valve ($269-25)
| Misc | [6 empty] | 4068.14
Pre 2: | Solar
Budget
6877.5 | Solar Solution |  |  | 2015-04-27 | 2133 | 2598.75 |  |  |  | Paper invoice
Actual | Solar Solution | [6 empty] | 2598.75 | 17325
2598.75 | Upfront SREC Credit | [7 empty] | -5250
| Solar Tax Credit | [7 empty] | -5197.5
Pre 3: | Miscellaneous
Budget
9400 | misc. tools | [7 empty] | 8000
Actual | trash - 10 pulls | 4 | 350 | [5 empty] | 1400
1 | General Requirements
Budget
2340
Actual
2340
| OMF Division 1: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 1170 | 1170
| OMF Division 1: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 1170 | 1170
[8 empty] | 2340 | 2340
2 | Demolition and Sitework
Budget
18240
Actual
18240
| OMF Division 2: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 10944 | 10944
| OMF Division 2: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 7296 | 7296
| OMF Division2: Return Deposit |  |  | 2015-12-17 | HELOC 8001 | -17400 | -17400 |  |  | http://www.vcs-va.com/
| OMF Division2: Deposit |  |  | 2015-12-17 | HELOC 8001 | 17400 | 17400
[8 empty] | 18240 | 18240
3 | Concrete
Budget
10916
Actual
10916
| OMF Division 3: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 10916 | 10916
[8 empty] | 10916 | 10916
4 | Masonry
Budget
17865
Actual
17865
| OMF Division 4: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 3573 | 3573
| OMF Division 4: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 14292 | 14292
[8 empty] | 17865 | 17865
5 | Metals
Budget
2341
Actual
0
OMF Division 5
[8 empty] | 0 | 2341
6 | Wood and Carpentry
Budget
78810
Actual
63048
| OMF Division 6: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 31524 | 31524
| OMF Division 6: Invoice 22265 |  |  | 2016-02-03 | HELOC 105 | 31524 | 31524
[8 empty] | 63048 | 78810
7 | Thermal and Moisture Protection
Budget
25128
Actual
20102.4
| OMF Division 6: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 20102.4 | 20102.4
[8 empty] | 20102.4 | 25128
8 | doors
Budget | interior doors
15360 | master bath new - 25"
Actual | Closet Doors
15360
| OMF Division 8: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 15360 | 15360
[8 empty] | 15360 | 15360
9 | Finishes and Accessories
Budget
21280
Actual
0
| Finishes and Accessories estimate from OMF | 1 | 15080 | [5 empty] | 15080 | mygirlsflooring.com, 301-861-0220
| tile - Neighbor Bryan | 400 | 8 | [5 empty] | 3200 | pale's roofing, 240-882-2078
http://carderock.com/tristatestone.html
3000
15 | Plumbing & Mechanical
Budget
54751.15
Actual
11041.15
| disconnect 2 AC units |  |  | 2015-12-11 | 2156 | 500 |  |  | 500 | 12/11: Allied Service Company
| ductwork: 1of2 payments |  |  | 2016-02-09 | HELOC 106 | 1500 |  |  |  | Allied Service Company, email agreement 2/8, $4400
| ductwork | [7 empty] | 4400
| reconnect 2 AC units | [7 empty] | 1000
| Air Conditioning | [6 empty] | 2000
| radiant floor heating | 1 | 13720 | [5 empty] | 13720 | 12/18: Estimate from Dave Glick from Aspen Hill plumbing $13,720, not including warmboard
| warmboard | 1000 | 7.79 | 2016-01-04 | HELOC cc | 500 |  |  | 7790 | 1/4: Provided drawings and paid design fee $500 by HELOC credit card. Receipt by email.
| central heating materials | 1 | 1041.15 |  |  | 1041.15 |  |  | 1041.15 | 3/19: See warmboard sheet. Online purchases from supplyhouse and pexuniverse. Tubing, manifolds, mixing valve, circulating pump, and tools
| radiator heating | 0 | 23040 | [5 empty] | 0 | 12/18: Estimate from Dave Glick from Aspen Hill plumbing $23,040
| Combo boiler/hot water | 1 | 7000 | 2015-12-21 | 8000 | 1500 |  |  | 7000 | 12/16: Paid $1500 of $3000 to Bob Gable from Allied Service Co. for plumbing work in foundation outside basement exit. Change in plans. No work in foundation. Tie into stack at kitchen and basement. Offered Bob $300 for saving $3000 if things hold up. | http://www.supplyhouse.com/Triangle-Tube-CC-125-96000-BTU-Output-Challenger-Combo-Boiler-Space-Heating-Domestic-Hot-Water
|  |  |  | 2016-01-11 | 103 | 6000 |  |  |  | Installed 1/7. Paper receipt
| Heating | [6 empty] | 9041.15
| toilets | 2 | 400 | [5 empty] | 800
| tub/shower | 1 | 500 | [5 empty] | 500
| luxury shower | 1 | 1000 | [5 empty] | 1000
| sink | 3 | 1000 | [5 empty] | 3000
| new tub | 2 | 1000 | [5 empty] | 2000
| service, drains, vents | 0 | 25750 | [5 empty] | 0 | 12/18: Estimate from Dave Glick at Aspen Hill Plumbing
| service, drains, vents | 1 | 12000 | [5 empty] | 12000 | 1/3: Bid from Bob Gable
| recirculating hot water | 0 | 1850 | [5 empty] | 0 | 12/18: Estimate from Dave Glick at Aspen Hill Plumbing
| Plumbing for bathrooms | [6 empty] | 0
16 | Electrical
Budget
22600 | Lights | 1 | 4000 | [5 empty] | 4000
Actual | Rudy Lopez Estimate | 1 | 14900 | 2016-01-05 | HELOC 102 | 7450 |  |  | 14900
11150 |  | 1 | 1000 | 2016-01-15 | HELOC 104 | 1000 |  |  | 1000
| Merrick Campbell Estimate | 0 | 22600 | [5 empty] | 0
| misc. elec | 1 | 2700 |  |  | 2700 |  |  | 2700 | 3/23/13: Joel Cruz
Pepco builders and inspectors Ken Murray: 202-331-6237, (fax 202-388-2721)
| Electrical | [6 empty] | 11150
MISC | MISC
Budget
0
Actual
2741.14
| Change Order 1, CMU walls at corners of 3rd floor: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 1200 | 1200
| Change Order 2, synthetic slate: Invoice 22275 |  |  | 2016-03-25 | HELOC 108 | 1300 | 1300
| Tools | 1 | 21.14 | 2016-01-09 | cc | 21.14
| Appliance Diagnostics | 1 | 100 | 2016-01-11 | 101 | 100
| Misc labor: demo and clean | 4 | 30 | 2016-03-12 | cash | 120
| Electrical | [6 empty] | 2741.14
| Total budget |  |  |  |  | 211902.6 | 150371.4 |  | 319326.79

## cash
Accounts | Updated 7/26/2015
| balance | rate | monthly payment
refinance | 121286.96
Schwab Brokerage | 28561
equity line | 67000 | 3% | 0.25% below prime
TSP loan | 50000 | 2.125% | 812
total liquid |  |  |  | 266847.96
prosper | 35383 |  |  | Stopped reinvesting on 7/7/15. Cash balance $3000 on 8/23. Cash available is $2000 per month
Schwab Inh IRA | 138629
Schwab Roth | 111367
TSP | 260000
FERS
total total |  |  |  | 812226.96
Debt | Updated 7/26/2015
| balance | rate | monthly payment
Mortgage | 405000 | 3.85% | 2632 | I can offset this (increase) by taking distributions from my Prosper account.
HELOC | 67000 | ?3.85? | 500 | I can offset this by taking distributions from my Prosper account.
TSP loan | 50000 | 2.125% | 812 | I can offset this by reducing TSP constributions (currently $660)
E: Student Loan | 30000 | 3% | 260
E: Car Loan | 23600 | 1.5% | 593
total | 575600 |  | 4797 | 575600
Income Retirement | Updated 7/26/2015
| balance | rate | monthly payment
TSP | 260000 |  | 1329 | $4800/month projected monthly payment assuming continued savings
Social Security |  |  | 2403 | Assuming work until 67. At 62 can receive $1566/month.
FERS |  |  | 2475 | Assuming work until 65. At 62 can receive 2235/month.
Charles Schwab Retirement Planning Calculator |  |  | https://client.schwab.com/Areas/Accounts/RetirementAssessment/YourInfo.aspx
Retirement age | 65
Life Expectancy | 90
Current salary | 134662
effective tax rate from paystub | 22.28%
Tax-advantaged retirement savings | 509996 |  | Includes TSP, Roth, and Schwab Inh IRA. Does not include FERS
Total amount you/your employer contribute annually | 29160 |  | From paystub (me+gov+gov) and IRA contribution
Taxable savings intended for retirement | 63944 |  | Includes prosper and brokerage
Yearly taxable savings for retirement | 0
Moderate-aggressive pre-retirement
Moderate-conservative after retirement
% current income, retirement spending |  | 100%
Soc Sec Ben |  |  | Calculate automatically. Begin receiving at 67
Retirement income | 0
Retirement Savings Projected | Report 7/26/2015 |  |  | 1720237
Retirement Savings Needed |  |  |  | 1380871
Surplus Retirement |  |  |  | 339366
Project Size
first | 1038 | 39400% | sf
second | 825 | 49000% | sf
total existing | 1863 | 88400% | sf
TOTAL BUILDING | 2747
$500/sf | 1373500

## WaterTight
Building Envelope
2015-07-25 | scheule for windows and doors sent and estimate requested
| steve | 84 LUMBER CO. #0913: | 5321 MARLBORO PIKE, UPPER MARLBORO, MD 20772 (17.36 mi) | 301-952-0584 | marinos@0913.84lumber.com
|  | LAMAR & WALLACE, INC. | 7000 OLD LANDOVER ROAD LANDOVER,MD 20785-1504 | 301-772-2400
|  | GALLIHER & HUGUELY ASSOCIATES, INC. | 5925 BLAIR RD. NW WASHINGTON,DC 20011-2343 | 202-723-1000
[12 empty] | total | 5.75% tax
| Windows |  | Jeld-Wen quote from Galliher & Hugueley | 5434.2176 | [7 empty] | 5138.74 | 295.4776
|  |  |  | Required | Provided |  |  | Need sash limiters
|  | Plans Pg A-0 | Energy Conservation | U-Factor = 0.35 | TBD |  |  | Quote based on 4-9/16" jambs.
|  | Plans Pg A-4 | Window and Exterior Door Schedule |  |  |  |  | what are the jamb sizes?
Floor | Room | ID in plans | Description and model from architect | Description and model from owner | Description and model from supplier | Planned width | Planned Height | Rough opening width | Rough opening height | # items | cost per item | total cost | delivery time
Third Floor | Bedroom | 1 | Jeld-Wen 2-3756 with 5-1/2" mull: Double Hung Window | Jeld-Wen: W-2500, Two Double Hung windows with 5.5" mull. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 78" | 54" | 76.25" | 56.75" | 1 | 740.75 | 740.75 | 3-4 weeks | s0122 | s0127 | Line 6 | mulled together
First Floor | Sun Room | 2.A1 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, Two mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" | 40.75" | 54.75" | 2 | 599.66 | 1199.32 | 3-4 weeks | s0106 | s0114 | Line 3
First Floor | Sun Room | 2.A2 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" |  |  | 0 |  | 0 | 3-4 weeks
First Floor | Sun Room | 2.A3 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, Two mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 96" |  |  | 0 |  | 0 | 3-4 weeks
First Floor | Sun Room | 2.A4 | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 42" | 96" |  |  | 0 |  | 0 | 3-4 weeks
Second Floor | Master Bath | 2.B | Jeld-Wen 2-2054 mulled together | Jeld-Wen: W-2500, 2 mulled casement windows, pushout, no grille, white | Jeld-Wen: see quote | 42" | 60" | 40.75" | 54.75" | 3 | 599.66 | 1798.98 | 3-4 weeks | s0145 | s0152 | Line 5
First Floor | Sun Room | 3 | Jeld-Wen 1754 fixed | Jeld-Wen: W-2500, one casement window, fixed, no grille, white | Jeld-Wen: see quote | 12" to 18" | 60" | 20.75" | 54.75" | 2 | 254.9 | 509.8 | 3-4 weeks | s0101 | s0105 | Line 1, Line 2
First Floor | Sun Room | 3 | Jeld-Wen 1754 fixed | Jeld-Wen: W-2500, one casement window, pushout, no grille, white | Jeld-Wen: see quote | 12" to 18" | 60" |  |  | 0 |  | 0 | 3-4 weeks
Third Floor | Bedroom | 4.A | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks | s0128 | s0133 | Line 7
Third Floor | Recreation room | 4.B | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks | s0128 | s0133 | Line 7
Third Floor | Bathroom | 4.C | Jeld-Wen 2956 | Jeld-Wen: W-2500, Double Hung window. Standard interior and exterior, no grille, white | Jeld-Wen: see quote | 30" | 54" | 30.125" | 56.75" | 1 | 296.63 | 296.63 | 3-4 weeks | s0153 | s0155
[12 empty] | total | 5.75% tax
| Doors |  | Lemieux, Masonite quote from Galliher & Hugueley | 2526.3675 | [7 empty] | 2389 | 137.3675
|  |  |  | Required | Provided |  |  | Can I remove T-astragal?
|  | Plans Pg A-0 | Energy Conservation | U-Factor = 0.35 | TBD |  |  | Quote based on 4-9/16" jambs.
what are the jamb sizes?
|  | Plans Pg A-4 | Window and Exterior Door Schedule
Floor | Room | ID in plans | Description and model from architect | Description and model from owner | Description and model from supplier | Planned width | Planned height | Width from supplier | Height from supplier | # items | cost per item | total cost | delivery time
Basement | Exit | A | Basement panel door with glass | Smooth-pro fiberglass panel exterior door, 1/2 view 9-light, 1-panel, screened | Masonite BLS-106-09I | 3' | 6'-8" | 3' | 6'-8" | 0 | 442 | 0 | 4-6 weeks
Basement | Exit | A.alternate | Basement panel door with glass | Authentic wood glass panel exterior door 5209 | Lemieux F5944 | 3' | 6'-8" | 3' | 6'-8" | 1 | 650 | 650 | 4-6 weeks
First Floor | Sun Room | B | Hinged patio door (inswing) Transom (3'x1') mulled above | Door from existing 2nd fl bedroom exit Security storm door from existing kitchen exit Transom (2'-6" x 1'-4") mulled above | Does current door with security storm door pass U-Factor? | 2'-6" | 6'-8" | 2'-6" | 6'-8" | 1 | 0 | 0 | EXISTING
First Floor | Sun Room | B.alternate | Hinged patio door (inswing) Transom (3'x1') mulled above | Hinged patio door (inswing) Transom (3'x1') mulled above | Lemieux 5001 W/Transom | 3' | 7' | 3' | 7' | 0 | 698 | 0 | 1-2 weeks
Third Floor | Exit To Balcony | C | Hinged patio door (inswing, 2-panel) | Authentic wood glass panel exterior door 5001 | Lemieux 5001 W/T-astragal | 6' | 6'-8" | 6' | 6'-8" | 1 | 949 | 949 | 1-2 weeks
Basement | Outside Under Sun Room | D | Paneled storage doors (inswing) | Smooth-pro fiberglass panel exterior door, 2-panel square top (match other basement door, no window) | Masonite 2-panel smooth fiberglass with T-astragal and slide bolt Can I remove the T-astragal? | 5' | 6'-8" | 5' | 6'-8" | 1 | 790 | 790 | 4-6 weeks
Roofs/Ceilings
Floor | Room | ID in plans | Desc | Detailed Description | Source and delivery |  |  | Width nominal (ft) | Height nominal (ft) | total (sf) | cost per sf: materials, supplies, tools |  | cost total
Estimates from | http://www.homewyse.com/
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | R-38 OR R-38C (10 1/4" HIGH DENSITY BATT) AT ATTIC AS ALLOWED BY EXISTING CLEARANCE, 2X8 rafters |  |  |  | 20 | 36 | 720 | 1.15 |  | 828
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | R-38 OR R-38C (10 1/4" HIGH DENSITY BATT) AT ATTIC AS ALLOWED BY EXISTING CLEARANCE, 2X8 rafters |  |  |  | 9 | 76 | 684 | 1.15 |  | 786.6
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Energy Conservation Insulation, Required R-Value = R-49 | 6 1/2" CLOSED CELL SPRAY FOAM (R38) ABOVE TOP PLATES AT EAVE, 2X8 rafters @ eaves |  |  |  | 8 | 16 | 128 | 1.15 |  | 147.2
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 20 | 36 | 720 | 3 |  | 2160 | homewyse says $3/sf for materials, tools, supplies
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 9 | 76 | 684 | 3 |  | 2052
Second floor | Flat roof | Plans Pg A-0 Plans A-5 | Roof liner | BLACK EPDM Rubber Roofing Membrane, 60 mil, 10x50 ft., |  |  |  | 8 | 16 | 128 | 3 |  | 384
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Fiberglass shingles |  |  |  |  | 9 | 76 | 684 | 3 |  | 2052
Third floor | Flat roof | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 20 | 36 | 720 | 0.5 |  | 360
Third floor | Mansard | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 9 | 76 | 684 | 0.5 |  | 342
Second floor | Flat roof | Plans Pg A-0 Plans A-5 | Sheathing Plywood |  |  |  |  | 8 | 16 | 128 | 0.5 |  | 64
Third floor | Roof/ceiling | Plans Pg A-0 Plans A-5 | Balcony floor | Duradek walkable floor membrane |  |  |  | 8 | 16 | 128 | 10.5 |  | 1344
Walls (Wood Framing)
|  |  |  | Required | Provided
|  |  | Energy Conservation | R-Value = R-20 or R-13+5 | R-21, 2X6 frame walls
Mass Walls
|  | Plans Pg A-0 | Energy Conservation, Required R-Value = R-8/13
Second floor | Master Bath | Plans Pg A-5
Basement Walls
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10/13 | N/A
Floors
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-19 | R-Value = R-30, 2X10 floor joists
Slab Perimeter R-value and Depth
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10, 2FT depth | N/A
Crawl Space
|  |  |  | Required | Provided
|  | Plans Pg A-0 | Energy Conservation | R-Value = R-10/13 | N/A
Infiltration
ALL EXTERIOR JOINTS SHALL HAVE A HIGH QUALITY DETAILED, AIR SEALING APPLIED TO INCLUDE BUT NOT LIMITED TO PICTURE FRAMING STUDS, BOTTOM PLATES, TOP PLATES, AROUND WINDOWS AND DOORS, EXHAUST PENETRATIONS, WIRING PENETRATIONS OSB GAPS, RIM JOISTS, AND NAIL-HOLES

## Flores
Original Bid |  | Water-tight Bid
1. DIVISION 1: General requirements | 17000 | 17000
2. DIVISION 2: Demolition and sitework | 15025 | 15025
3. DIVISION 3: Concrete | 8500 | 8500
4. DIVISION 4: Masonry | 13125 | 13125
5. DIVISION 5: Metals | 1800
6. DIVISION 6: Wood/ Carpentry | 65075 | 65075
7. DIVISION 7: Thermal and moister protection | 19840 | 19840 | This is an overestimate because it does not include insulation.
8. DIVISION 8: Doors and windows | 14300 | 14300
9. DIVISION 9: Finishes and accessories | 15080
10. DIVISION 10 -14: Not included | 0
11. DIVISION 15: Plumbing and Mechanical | 32000 | 1000 | This is an uneducated guess.
12. DIVISION 16: Electrical | 15500
13. ALLOWANCES: | 10240
 Ceramic tile – 360 Sf @ $ 7.50 p/Sf = $ 2,700.00 |  | 0
 Counter top slab – 16 Sft @ $ 65.00 = $ 1,040.00 |  | 0
 Plumbing fixtures and bath accessories - $ 5,000.00 |  | 0
 Bath vanities for powder room and master bath - $ 1,500.00 |  | 0
0
TOTAL | 227485 | 153865
14. OVERHEAD AND PROFIT- 20% | 45497 | 30773
Compare to
GRAND TOTAL | 272982 | 184638 | 174000

## warmboard
Approved tubing list at the bottom
PEX Tubing Calculator
1. What is the total square footage of the area you want to cover? | [6 empty] | 1000 Sq. Ft.
2. How many inches apart will the loops be spaced? Learn More | [6 empty] | 8 inches
You will need 1,500 ft of oxygen barrier PEX tubing. | [6 empty] | 1500 Ft
http://www.moen.com/connection-types | Plumbing connections |  |  | IPS is a threaded connection type.
http://www.supplyhouse.com/resources/pexConnections | Pex compression fitting Connections |  |  | Compression fittings may be used to make connections for PEX and PEX-AL-PEX tubing. Compression fittings do not require a special tool.
http://s3.supplyhouse.com/product_files/Uponor-A6140750-sizing-guide.pdf | Pipe sizing guide
TUBING | location |  |  |  | URL | supplier | Qty Ft | total cost
1/2" hePEX - (500 ft. coil) SKU:A1260500 Brand: Uponor (Wirsbo) | in boards |  |  |  | http://www.supplyhouse.com/Wirsbo-Uponor-A1260500-1-2-hePEX-plus-500-ft-coil | supply house | 1500 | 844.85 | 5 stars | 73 reviews
1/2" PEX-AL-PEX Tubing (1,000 ft Coil) SKU:050-1000-PAP Brand: Rifeng | in boards |  |  |  | http://www.supplyhouse.com/Rifeng-050-1000-PAP-1-2-PEX-AL-PEX-Tubing-1000-ft-Coil | supply house | 1500 | 561.85 | 5 stars | 17 reviews
1/2" x 1000ft PEX-AL-PEX Tubing Everhot Brand: Everhot Mfr Part#: APX1210 | in boards |  |  |  | http://www.pexuniverse.com/apx1210-1-2-x-1000ft-pex-al-pex-tubing | pexuniverse | 1500 | 506.9 | unrated
3/4" Pre-Insulated Wirsbo hePEX w/ 1/2" Insulation, 100 ft coil SKU:A6140750, Brand: Uponor (Wirsbo) | to/from manifold |  |  |  | http://www.supplyhouse.com/Uponor-Wirsbo-A6140750-3-4-Pre-Insulated-Wirsbo-hePEX-w-1-2-Insulation-100-ft-coil | supply house | 100 | 269.95
7/8" Pipe (O.D.) x 1/2" Wall Insul-Lock Pipe Insulation, 6' | for 3/4" copper pipe to/from basement and 3rd floor |  |  |  | http://www.supplyhouse.com/K-Flex-6RXL048078-7-8-Pipe-OD-x-1-2-Wall-Insul-Lock-Pipe-Insulation-6 | supply house | 40 | 52.3333
Manifolds | location | supply return type | pex type |  | URL | supplier |  | total cost
3 Loop Stainless Steel Manifold Package - 1/2" PEX-AL-PEX | 3rd floor | 1", BSP | 1/2" |  | http://www.supplyhouse.com/Rifeng-RHM03-50PAPK-3-Loop-Stainless-Steel-Manifold-Package-1-2-PEX-AL-PEX |  |  | 138.95
3-branch Stainless Steel Radiant Heat Manifold Set w/ 1/2" PEX adapters Brand: Rifeng Mfr Part#: SSM103 | 3rd floor | 1" IPS (iron pipe straight) threaded ball valve | 1/2" 5/8" adapters available | Pex compression-style adapters | http://www.pexuniverse.com/ssm103-steel-radiant-heat-manifold |  |  | 122.95 |  | On user guide: What is G1" connection?
2-branch Stainless Steel Radiant Heat Manifold Set w/ 1/2" PEX adapters, Brand: Rifeng, Mfr Part#: SSM102 | basement | 1" NPT (national pipe tapered) threaded ball valve |  | Pex compression-style adapters | http://www.pexuniverse.com/ssm102-steel-radiant-heat-manifold |  |  | 101.95
3 Loop Stainless Steel PEX Manifold with 1/2" Connectors w/ Automatic Purge Valve | 3rd fl and basement | 1" NPT threaded ball valve | 1/2" 5/8" adapters available |  | http://www.pexsuperstore.com/pex-manifolds/radiant-pex-manifolds/connectors/3-loop-stainless-steel-pex-manifold-with-1-2-inch-connectors.html |  |  | 122.95
3-Loop 1" Stainless Steel Radiant Heat Manifold Assembly w/ Flow Meter SKU:A2700302 Brand: Uponor (Wirsbo) | 3rd fl and basement | 1" NPT threaded ball valve | 1/2" 5/8" requies 6 loop fitting assemblies | PEX compression, PEX-AL-PEX compression | http://www.supplyhouse.com/Uponor-Wirsbo-A2700302-3-Loop-1-Stainless-Steel-Radiant-Heat-Manifold-Assembly-w-Flow-Meter |  |  | 219.95
Mixing Valve | location | supply return type | pex type |  | URL | supplier |  | total cost
1/2" PEX Union 5002 Heating Only Mixing Valve
1/2" NPT Mixing Valve, Lead Free (70°F-145°F), SKU:AM100-1LF |  |  |  | requires adaptor below | http://www.supplyhouse.com/Honeywell-Sparco-AM100-1LF-1-2-NPT-Mixing-Valve-Lead-Free-70176F-145176F |  |  | 80.95
1/2" PEX-AL-PEX Compression x 1/2" Male Threaded Adapter, SKU:PAP-0500M |  |  |  | adaptor | http://www.supplyhouse.com/Rifeng-PAP-0500M-1-2-PEX-AL-PEX-Compression-x-1-2-Male-Threaded-Adapter |  |  | 2.56
1" Thermostatic Mixing Valve 80 to 165°F, Lead Free (Union Sweat) |  |  |  |  | http://www.supplyhouse.com/Zurn-1-ZW1017XLHTC-1-Thermostatic-Mixing-Valve-80-to-165F-Lead-Free-Union-Sweat |  |  | 139.95
Circulating pump | location | supply return type | pex type |  | URL | supplier |  | total cost
Requirements:
Star S 21F, 3-Speed Cast Iron Star Series Circulator, 1/12 HP, SKU:4105032, Brand: Wilo |  |  |  |  | http://www.supplyhouse.com/Wilo-4105032-Star-S-21F-3-Speed-Cast-Iron-Star-Series-Circulator-1-12-HP |  |  | 75.95
Misc | location | supply return type | pex type |  | URL | supplier |  | total cost
PEX-al-PEX Chamfering Tool (1/2", 3/4", 1"), SKU:8220875, Brand: Mr. PEX |  |  |  |  | http://www.supplyhouse.com/Mr-PEX-8220875-PEX-al-PEX-Chamfering-Tool-1-2-3-4-1 |  |  | 18.55
Tube Cutter, (plastic) up to 1" PEX, SKU:E6081128, Brand: Uponor (Wirsbo) |  |  |  |  | http://www.supplyhouse.com/Wirsbo-Uponor-E6081128-Tube-Cutter-plastic-up-to-1-PEX-2165000-p |  |  | 19.95
1041.15
Approved tubing list 4
Pex Aluminum Pex tubing 1/2" ID
y AIM: Pex AL Pex
y Allied Pipe Systems: Pex AL Pex
y Aqua Therm: Pex AL Pex
y ComfortPro: Pex AL Pex
y EHT (Efficient Heating Technology): Pex AL Pex
y Everhot: Pex AL Pex
y Excel: Pex AL Pex
y Henco: Pex AL Pex
y Hydro-flex: Pex AL Pex
y HYDRONX: Pex AL Pex
y Inferno: Pex AL Pex
y Infloor Heating Systems: Pex AL Pex
y Mr. Pex: Pex AL Pex
y RHT: Pex AL Pex
y Rifeng: Pex AL Pex
y Roth: Pex AL Pex
y Uponor: Multi-Layer composite tubing (MLC)
Pex AL Pex
y Watts: Pex AL Pex
y Weil-McLain: Pex AL Pex
y WSD (Willow Springs Distributing) Pex AL Pex
y Zurn Alumicor: Pex AL Pex
Standard Barrier Pex 1/2" tubing ID
y Mr. Pex (LK Pex AB)
y Rehau Raupex Oxygen barrier manufactured after
3/8/11-date printed on tubing
y ThermaPEX (LK PEX)
y Uponor Wirsbo hePEX
y ViegaPEX Barrier
y Watts RadiantPEX+

## Staircase
Loudoun Stairs / 540-338-7400
Century Stair Company / 703-753-3912
Southern Staircase / 800-874-8408